## Work Report
WEEKLY UNITS COMPLETED PER SCOPE ID
Report Generated On: 08/18/2025 09:48 PM
| REPORT SUMMARY |  |  |  | REPORT DETAILS
| Total Billed Amount: | 0 |  |  | Foreman: | Devin Carriere
| Total Line Items: | 270 |  |  | Work Request #: | 89713058
| Billing Period: | 08/04/2025 to 08/10/25 |  |  | Scope ID #: | R25P16
[5 empty] | Work Order #: | DCP0371565
[5 empty] | Customer: | AEP
[5 empty] | Job #: | 820-1
Friday (08/08/2025)
Point Number | Billable Unit Code | Work Type | Unit Description | Unit of Measure | # Units | N/A | Pricing
Point 15 | ARM-8SF-GN-TL-C | Inst | ARM,8ft Sgl.Fiberglass,Gain,Tang LD,Corr | EA | 0 |  | 0
Point 15 | BKT-AC243PH-F-C | Inst | BKT,Riser Arr/Term 24in 3Ph,Fbrgls,Corr | EA | 0 |  | 0
Point 15 | BKT-CMX-50-A | Inst | BKT,Cluster Mnt (XFMR),50KVA,Alum | EA | 0 |  | 0
TOTAL | [6 empty] | 0
Saturday (08/09/2025)
Point Number | Billable Unit Code | Work Type | Unit Description | Unit of Measure | # Units | N/A | Pricing
Point 05 | BKT-AC24-F-C | Inst | BKT,Arrestor/CO 24in (1Ph),Fbrgls,Corr | EA | 1 |  | 0
Point 05 | BKT-IP8-F-C | Inst | BKT,Insulator Post 8in,Fbrgls,Corrosive | EA | 1 |  | 0
Point 05 | BKT-PI18-F | Inst | BKT,Pin insulator 18in,Fbrgls | EA | 1 |  | 0
Point 05 | CNC-SNB-2 | Inst | CNC,Splice Non-Tension Bare,#6-#2 | EA | 1 |  | 0
Point 05 | CNC-SNB-40 | Inst | CNC,Splice Non-Tension Bare,#1/0-#4/0 | EA | 1 |  | 0
Point 05 | CND-HLC2 | Inst | CND,Hot Line clamp #6-#2 | EA | 1 |  | 0
Point 05 | CND-S2O | Inst | CND,Stirrup #2 Open | EA | 1 |  | 0
Point 05 | DEG-10-SPA | Inst | DEG,1/0,Slack Span Alum | EA | 2 |  | 0
Point 05 | EQL-1-4-C-4-C-LC1 | Inst | EQL,1 Phase,#4,Sol,#4,Sol,100a C/O | EA | 1 |  | 0
Point 05 | SWI-27-CO1-100-H-C | Inst | SWI,27kV,Line Cutout 1PH,100A,Hook,C | EA | 1 |  | 0
Point 06 | ARM-8S-60S | Rem | ARM,8ft Single Wood,60in Sgl.Wd | EA | 1 |  | 0
Point 06 | BKT-PI18-F | Rem | BKT,Pin insulator 18in,Fbrgls | EA | 1 |  | 0
Point 06 | CND-HLC2 | Rem | CND,Hot Line clamp #6-#2 | EA | 1 |  | 0
Point 06 | CND-S2O | Rem | CND,Stirrup #2 Open | EA | 1 |  | 0
Point 06 | DEG-2-SPA | Rem | DEG,#2,Slack Span Alum | EA | 2 |  | 0
Point 06 | INS-15-P-S-C | Rem | INS,15kV,Pin,Silicon Polymer,Corr | EA | 5 |  | 0
Point 06 | PIN-XAL-C | Rem | Pin,Crossarm Light,Corrosive | EA | 3 |  | 0
Point 06 | POL-40-3 | Rem | Pole,40ft,Class 3 | EA | 0 |  | 0
Point 06 | SAA-3-CV-C | Rem | SAA,3 inch,Clevis,Corr | EA | 2 |  | 0
Point 07 | CON-10-AAA-1-B | Inst | CON,#1/0 AWG,Alum Alloy,One,Bare | FT | 51 |  | 0
Point 07 | INS-15-P-S-C | Inst | INS,15kV,Pin,Silicon Polymer,Corr | EA | 1 |  | 0
Point 07 | PIN-15-PTP-C | Inst | Pin,15kV,Pole top,Corrosive | EA | 1 |  | 0
Point 07 | SAA-3-CV-C | Inst | SAA,3 inch,Clevis,Corr | EA | 1 |  | 0
Point 07 | TIE-4-ALH-F | Inst | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 08 | INS-15-P-S-C | Rem | INS,15kV,Pin,Silicon Polymer,Corr | EA | 1 |  | 0
Point 08 | PIN-15-PTP-C | Rem | Pin,15kV,Pole top,Corrosive | EA | 1 |  | 0
Point 08 | POL-40-4 | Rem | Pole,40ft,Class 4 | EA | 0 |  | 0
Point 08 | SAA-3-CV-C | Rem | SAA,3 inch,Clevis,Corr | EA | 1 |  | 0
Point 09 | ANC-DHM-10-84-T1-C | Inst | ANC,Dbl Hlx Mach,10in,84in,TpEye 1in,Cor | EA | 1 |  | 0
Point 09 | CNC-SNB-40 | Inst | CNC,Splice Non-Tension Bare,#1/0-#4/0 | EA | 2 |  | 0
Point 09 | CON-10-AAA-1-B-REEL | Inst | CON,#1/0 AWG,Alum Alloy,One,Bare,Reel | FT | 179 |  | 0
Point 09 | CON-2-AAA-1-B-REEL | Inst | CON,#2 AWG,Alum Alloy,One,Bare,Reels | FT | 179 |  | 0
Point 09 | DEC-20AL-C | Inst | DEC,#4 - #2/0 AA,AL,AS,Corrosive | EA | 1 |  | 0
Point 09 | DEG-10-PNA | Inst | DEG,1/0,Primary Neutral Al | EA | 1 |  | 0
Point 09 | DEG-10-SPA | Inst | DEG,1/0,Slack Span Alum | EA | 2 |  | 0
Point 09 | GYD-MPY | Inst | GYD,Marker-Plastic-Yellow | EA | 1 |  | 0
Point 09 | GYF-38-78W-IL-C | Inst | GYF,3/8,78"WireMt,Insltr&Link Adder,Corr | EA | 1 |  | 0
Point 09 | GYF-38-D-42P-EP-C | Inst | GYF,3/8,Down,42in Pole mt,EyePlate,Corr | EA | 1 |  | 0
Point 09 | GYF-38-D-78P-EP-C | Inst | GYF,3/8,Down,78in Pole mt,EyePlate,Corr | EA | 1 |  | 0
Point 09 | GYW-38C | Inst | GYW,3/8 in. Corrosive (16,200 lbs) | FT | 80 |  | 0
Point 09 | INS-15-D-S-C | Inst | INS,15kV,Deadend,Polymer,Corr | EA | 1 |  | 0
Point 09 | INS-15-P-S-C | Inst | INS,15kV,Pin,Silicon Polymer,Corr | EA | 1 |  | 0
Point 09 | PIN-15-PTP-C | Inst | Pin,15kV,Pole top,Corrosive | EA | 1 |  | 0
Point 09 | PLD-EYE-C | Inst | PLD,Eyebolt Deadend,Corrosive | EA | 2 |  | 0
Point 09 | POL-40-2 | Inst | Pole,40ft,Class 2 | EA | 1 |  | 0
Point 09 | SAA-3-CV-C | Inst | SAA,3 inch,Clevis,Corr | EA | 1 |  | 0
Point 09 | SAA-DE-20-C | Inst | SAA,DE Clamp #4-2/0, Corr. | EA | 1 |  | 0
Point 09 | SAA-DI-10-C | Inst | SAA,Dead End I Bolt,1/0,Corr | EA | 1 |  | 0
Point 09 | SVC-10-TP-AAA-RS | Tran | SVC,1/0,Trip,All Alum,Res | EA | 1 |  | 0
Point 09 | SVC-VA | Inst | SVC-Virtual Asset Capitalization | EA | 1 |  | 0
Point 09 | SVD-3-CV | Inst | SVD,3 inch,Clevis | EA | 1 |  | 0
Point 09 | SVD-SG10 | Inst | SVD, Service Grip, 1/0 | EA | 1 |  | 0
Point 10 | ANC-DHM-10-84-T1-C | Rem | ANC,Dbl Hlx Mach,10in,84in,TpEye 1in,Cor | EA | 1 |  | 0
Point 10 | CON-2-AAA-1-B-REEL | Rem | CON,#2 AWG,Alum Alloy,One,Bare,Reels | FT | 290 |  | 0
Point 10 | DEC-20AL-C | Rem | DEC,#4 - #2/0 AA,AL,AS,Corrosive | EA | 1 |  | 0
Point 10 | DEG-2-SPA | Rem | DEG,#2,Slack Span Alum | EA | 2 |  | 0
Point 10 | GYD-MPY | Rem | GYD,Marker-Plastic-Yellow | EA | 1 |  | 0
Point 10 | GYF-38-42W-I-C | Rem | GYF,3/8,42In Wire Mt,InsulatorAdder,Corr | EA | 1 |  | 0
Point 10 | GYF-38-D-42P-EP-C | Rem | GYF,3/8,Down,42in Pole mt,EyePlate,Corr | EA | 1 |  | 0
Point 10 | GYW-38C | Rem | GYW,3/8 in. Corrosive (16,200 lbs) | FT | 40 |  | 0
Point 10 | INS-15-D-S-C | Rem | INS,15kV,Deadend,Polymer,Corr | EA | 1 |  | 0
Point 10 | INS-15-P-S-C | Rem | INS,15kV,Pin,Silicon Polymer,Corr | EA | 1 |  | 0
Point 10 | PIN-15-PTP-C | Rem | Pin,15kV,Pole top,Corrosive | EA | 1 |  | 0
Point 10 | PLD-EYE-C | Rem | PLD,Eyebolt Deadend,Corrosive | EA | 2 |  | 0
Point 10 | POL-40-5 | Rem | Pole,40ft,Class 5 | EA | 0 |  | 0
Point 10 | SAA-3-CV-C | Rem | SAA,3 inch,Clevis,Corr | EA | 1 |  | 0
Point 10 | SAA-DE-20-C | Rem | SAA,DE Clamp #4-2/0, Corr. | EA | 1 |  | 0
Point 10 | SVC-10-TP-AAA-RS | Rem | SVC,1/0,Trip,All Alum,Res | EA | 1 |  | 0
Point 10 | SVC-VA | Rem | SVC-Virtual Asset Capitalization | EA | 1 |  | 0
Point 10 | SVD-3-CV | Rem | SVD,3 inch,Clevis | EA | 1 |  | 0
Point 10 | SVD-SG10 | Rem | SVD, Service Grip, 1/0 | EA | 1 |  | 0
Point 11 | CON-10-AAA-1-B-REEL | Inst | CON,#1/0 AWG,Alum Alloy,One,Bare,Reel | FT | 178 |  | 0
Point 11 | CON-2-AAA-1-B-REEL | Inst | CON,#2 AWG,Alum Alloy,One,Bare,Reels | FT | 178 |  | 0
Point 11 | GND-CR-4 | Inst | GND,Cu Clad Rod,#4 | EA | 1 |  | 0
Point 11 | INS-15-P-S-C | Inst | INS,15kV,Pin,Silicon Polymer,Corr | EA | 1 |  | 0
Point 11 | PIN-15-PTP-C | Inst | Pin,15kV,Pole top,Corrosive | EA | 1 |  | 0
Point 11 | POL-40-2 | Inst | Pole,40ft,Class 2 | EA | 1 |  | 0
Point 11 | SVD-SG10 | Inst | SVD, Service Grip, 1/0 | EA | 3 |  | 0
Point 12 | CON-2-AAA-1-B-REEL | Rem | CON,#2 AWG,Alum Alloy,One,Bare,Reels | FT | 338 |  | 0
Point 13 | ANC-DHM-10-84-T1-C | Inst | ANC,Dbl Hlx Mach,10in,84in,TpEye 1in,Cor | EA | 1 |  | 0
Point 13 | BKT-AC24-F-C | Inst | BKT,Arrestor/CO 24in (1Ph),Fbrgls,Corr | EA | 1 |  | 0
Point 13 | CND-HLC2 | Inst | CND,Hot Line clamp #6-#2 | EA | 1 |  | 0
Point 13 | CND-S2O | Inst | CND,Stirrup #2 Open | EA | 1 |  | 0
Point 13 | DEC-20AL-C | Inst | DEC,#4 - #2/0 AA,AL,AS,Corrosive | EA | 1 |  | 0
Point 13 | DEG-10-PNA | Inst | DEG,1/0,Primary Neutral Al | EA | 2 |  | 0
Point 13 | EQL-1-4-C-20-S-X-C | Inst | EQL,1 Ph,#4,CU Sol,2/0,CU Str,Xfr,Corr | EA | 1 |  | 0
Point 13 | GND-CR-4 | Inst | GND,Cu Clad Rod,#4 | EA | 1 |  | 0
Point 13 | GYD-MPY | Inst | GYD,Marker-Plastic-Yellow | EA | 1 |  | 0
Point 13 | GYF-38-78W-IL-C | Inst | GYF,3/8,78"WireMt,Insltr&Link Adder,Corr | EA | 1 |  | 0
Point 13 | GYF-38-D-78P-EP-C | Inst | GYF,3/8,Down,78in Pole mt,EyePlate,Corr | EA | 1 |  | 0
Point 13 | GYW-38C | Inst | GYW,3/8 in. Corrosive (16,200 lbs) | FT | 40 |  | 0
Point 13 | INS-15-D-S-C | Inst | INS,15kV,Deadend,Polymer,Corr | EA | 1 |  | 0
Point 13 | PLD-EYE-C | Inst | PLD,Eyebolt Deadend,Corrosive | EA | 2 |  | 0
Point 13 | POL-40-2 | Inst | Pole,40ft,Class 2 | EA | 1 |  | 0
Point 13 | SAA-3-CV-C | Inst | SAA,3 inch,Clevis,Corr | EA | 2 |  | 0
Point 13 | SAA-DE-20-C | Inst | SAA,DE Clamp #4-2/0, Corr. | EA | 1 |  | 0
Point 13 | SVC-2-TP-AAA-RS | Tran | SVC, #2 AWG ,Trip,Alum/Alloy Neut,RS | EA | 4 |  | 0
Point 13 | SVC-VA | Inst | SVC-Virtual Asset Capitalization | EA | 4 |  | 0
Point 13 | SVD-3-CV-C | Inst | SVD,3 inch,Clevis,Corr | EA | 2 |  | 0
Point 13 | SVD-SG2 | Inst | SVD,Service Grip,#2 | EA | 4 |  | 0
Point 13 | XCO-27-100-8-C | Inst | XCO,27kV Polymer,100 Amp,8kA, Corrosive | EA | 1 |  | 0
Point 13 | XFR-50-72-120-1B | Tran | XFR,50KVA,7.2/12.4kVY,120/240,1BG | EA | 1 |  | 0
Point 14 | ANC-DHM-10-84-T1-C | Rem | ANC,Dbl Hlx Mach,10in,84in,TpEye 1in,Cor | EA | 1 |  | 0
Point 14 | BKT-AC18-F | Rem | BKT,Arrestor/CO 18in (1Ph),Fbrgls | EA | 1 |  | 0
Point 14 | DEC-20AL-C | Rem | DEC,#4 - #2/0 AA,AL,AS,Corrosive | EA | 1 |  | 0
Point 14 | EQL-1-4-C-2-S-X-C | Rem | EQL,1 Ph,#4,CU Sol,#2,CU Str,Xfr,Corr | EA | 1 |  | 0
Point 14 | GND-CR-4 | Rem | GND,Cu Clad Rod,#4 | EA | 1 |  | 0
Point 14 | GYD-MPY | Rem | GYD,Marker-Plastic-Yellow | EA | 1 |  | 0
Point 14 | GYF-38-42W-I-C | Rem | GYF,3/8,42In Wire Mt,InsulatorAdder,Corr | EA | 1 |  | 0
Point 14 | GYF-38-D-42P-EP-C | Rem | GYF,3/8,Down,42in Pole mt,EyePlate,Corr | EA | 1 |  | 0
Point 14 | GYW-38C | Rem | GYW,3/8 in. Corrosive (16,200 lbs) | FT | 40 |  | 0
Point 14 | INS-15-D-S-C | Rem | INS,15kV,Deadend,Polymer,Corr | EA | 1 |  | 0
Point 14 | PLD-EYE-C | Rem | PLD,Eyebolt Deadend,Corrosive | EA | 2 |  | 0
Point 14 | POL-40-4 | Rem | Pole,40ft,Class 4 | EA | 0 |  | 0
Point 14 | SAA-DE-20-C | Rem | SAA,DE Clamp #4-2/0, Corr. | EA | 1 |  | 0
Point 14 | XCO-27-100-8-C | Rem | XCO,27kV Polymer,100 Amp,8kA, Corrosive | EA | 1 |  | 0
Point 08 | PLA-CUT | Inst | PLA,Cut Off Pole Top | EA | 1 |  | 0
Point 06 | PLA-CUT | Inst | PLA,Cut Off Pole Top | EA | 1 |  | 0
Point 10 | PLA-CUT | Inst | PLA,Cut Off Pole Top | EA | 1 |  | 0
Point 14 | PLA-CUT | Inst | PLA,Cut Off Pole Top | EA | 1 |  | 0
TOTAL | [6 empty] | 0
Sunday (08/10/2025)
Point Number | Billable Unit Code | Work Type | Unit Description | Unit of Measure | # Units | N/A | Pricing
Point 01 | BKT-ARML-A-C | Inst | BKT,Crossarm inLin,Alum,Corr | EA | 3 |  | 0
Point 02 | POL-45-3 | Rem | Pole,45ft,Class 3 | EA | 1 |  | 0
Point 02 | SAA-3-CV-C | Rem | SAA,3 inch,Clevis,Corr | EA | 1 |  | 0
Point 02 | SAA-DE-20-C | Rem | SAA,DE Clamp #4-2/0, Corr. | EA | 1 |  | 0
Point 03 | BKT-AC243PH-F-C | Inst | BKT,Riser Arr/Term 24in 3Ph,Fbrgls,Corr | EA | 1 |  | 0
Point 03 | BKT-CMX-167-A | Inst | BKT,Cluster Mnt (XFMR),167KVA,Alum | EA | 1 |  | 0
Point 03 | BKT-IP8-F | Inst | BKT,Insulator Post 8in,Fbrgls | EA | 1 |  | 0
Point 03 | EQL-1-40-S-XP | Inst | EQL,1ph,40 Cu,Stranded,Xfmr Parallel | EA | 3 |  | 0
Point 03 | EQL-3-4-C-40-S-X | Inst | EQL,3 Ph,#4,CU Sol,4/0,CU Str,Xfr | EA | 1 |  | 0
Point 03 | SVC-40-TP-ALA-CC | Tran | SVC,4/0,Trip,Alum/Aly Neut,Corr/Comm | EA | 3 |  | 0
Point 03 | SVC-VA | Inst | SVC-Virtual Asset Capitalization | EA | 3 |  | 0
Point 03 | SVD-DI-40-C | Inst | SVD,Dead End I Bolt,4/0,Corr | EA | 3 |  | 0
Point 03 | TIE-4-ALH-F | Inst | TIE,4 AWG,AL Hand Tie,F Neck | EA | 24 |  | 0
Point 03 | TIE-4-CUH-15 | Inst | TIE,4 AWG,CU Hand Tie,15kV (F Neck) | EA | 8 |  | 0
Point 03 | XCO-27-100-8-C | Inst | XCO,27kV Polymer,100 Amp,8kA, Corrosive | EA | 3 |  | 0
Point 03 | XFR-100-72-120-2B-S | Tran | XFR,100KVA,7.2/12.4kVY,120/240,2BG,SS | EA | 3 |  | 0
Point 04 | ARM-8S-60S | Rem | ARM,8ft Single Wood,60in Sgl.Wd | EA | 1 |  | 0
Point 04 | BKT-AC183PH-F-C | Rem | BKT,Riser Arr/Term 18in 3Ph,Fbrgls,Corr | EA | 1 |  | 0
Point 04 | BKT-CMX-167-A | Rem | BKT,Cluster Mnt (XFMR),167KVA,Alum | EA | 1 |  | 0
Point 04 | BKT-IP8-F-C | Rem | BKT,Insulator Post 8in,Fbrgls,Corrosive | EA | 1 |  | 0
Point 04 | EQL-1-40-S-XP | Rem | EQL,1ph,40 Cu,Stranded,Xfmr Parallel | EA | 3 |  | 0
Point 04 | EQL-3-4-C-40-S-X | Rem | EQL,3 Ph,#4,CU Sol,4/0,CU Str,Xfr | EA | 1 |  | 0
Point 04 | GND-CR-4 | Rem | GND,Cu Clad Rod,#4 | EA | 1 |  | 0
Point 04 | INS-15-P-S-C | Rem | INS,15kV,Pin,Silicon Polymer,Corr | EA | 4 |  | 0
Point 04 | PIN-XAL-C | Rem | Pin,Crossarm Light,Corrosive | EA | 3 |  | 0
Point 04 | POL-45-3 | Rem | Pole,45ft,Class 3 | EA | 0 |  | 0
Point 04 | SAA-3-CV-C | Rem | SAA,3 inch,Clevis,Corr | EA | 6 |  | 0
Point 04 | SVC-VA | Rem | SVC-Virtual Asset Capitalization | EA | 3 |  | 0
Point 04 | SVD-DI-40-C | Rem | SVD,Dead End I Bolt,4/0,Corr | EA | 3 |  | 0
Point 04 | XCO-27-100-8-C | Rem | XCO,27kV Polymer,100 Amp,8kA, Corrosive | EA | 3 |  | 0
Point 15 | BKT-IP8-F-C | Inst | BKT,Insulator Post 8in,Fbrgls,Corrosive | EA | 0 |  | 0
Point 15 | CND-HLC2 | Inst | CND,Hot Line clamp #6-#2 | EA | 0 |  | 0
Point 15 | CND-S2O | Inst | CND,Stirrup #2 Open | EA | 0 |  | 0
Point 15 | EQL-3-4-C-40-S-X | Inst | EQL,3 Ph,#4,CU Sol,4/0,CU Str,Xfr | EA | 0 |  | 0
Point 15 | GND-CR-4 | Inst | GND,Cu Clad Rod,#4 | EA | 0 |  | 0
Point 15 | GND-MD | Inst | GND,Wire Mldg Only | EA | 0 |  | 0
Point 15 | INS-15-P-S-C | Inst | INS,15kV,Pin,Silicon Polymer,Corr | EA | 0 |  | 0
Point 15 | PIN-15-PTP-C | Inst | Pin,15kV,Pole top,Corrosive | EA | 0 |  | 0
Point 15 | PIN-XAL-C | Inst | Pin,Crossarm Light,Corrosive | EA | 0 |  | 0
Point 15 | POL-45-2 | Inst | Pole,45ft,Class 2 | EA | 0 |  | 0
Point 15 | SAA-3-CV-C | Inst | SAA,3 inch,Clevis,Corr | EA | 0 |  | 0
Point 15 | TIE-4-ALH-F | Inst | TIE,4 AWG,AL Hand Tie,F Neck | EA | 24 |  | 0
Point 15 | TIE-4-CUH-15 | Inst | TIE,4 AWG,CU Hand Tie,15kV (F Neck) | EA | 8 |  | 0
Point 15 | XCO-27-100-8-C | Inst | XCO,27kV Polymer,100 Amp,8kA, Corrosive | EA | 0 |  | 0
Point 15 | XFR-50-72-120CUT-1B | Tran | XFR,50KVA,7.2/12.4kVY,120 CUTOVER,1BG | EA | 0 |  | 0
Point 16 | ARM-8S-60S | Rem | ARM,8ft Single Wood,60in Sgl.Wd | EA | 0 |  | 0
Point 16 | BKT-AC183PH-F-C | Rem | BKT,Riser Arr/Term 18in 3Ph,Fbrgls,Corr | EA | 0 |  | 0
Point 16 | BKT-CMX-50-A | Rem | BKT,Cluster Mnt (XFMR),50KVA,Alum | EA | 0 |  | 0
Point 16 | BKT-IP8-F-C | Rem | BKT,Insulator Post 8in,Fbrgls,Corrosive | EA | 0 |  | 0
Point 16 | EQL-3-4-C-40-S-X | Rem | EQL,3 Ph,#4,CU Sol,4/0,CU Str,Xfr | EA | 0 |  | 0
Point 16 | GND-CR-4 | Rem | GND,Cu Clad Rod,#4 | EA | 0 |  | 0
Point 16 | INS-15-P-S-C | Rem | INS,15kV,Pin,Silicon Polymer,Corr | EA | 0 |  | 0
Point 16 | PIN-XAL-C | Rem | Pin,Crossarm Light,Corrosive | EA | 0 |  | 0
Point 16 | POL-40-2 | Rem | Pole,40ft,Class 2 | EA | 0 |  | 0
Point 16 | SAA-3-CV-C | Rem | SAA,3 inch,Clevis,Corr | EA | 0 |  | 0
Point 16 | TIE-4-ALH-F | Rem | TIE,4 AWG,AL Hand Tie,F Neck | EA | 0 |  | 0
Point 16 | TIE-4-CUH-15 | Rem | TIE,4 AWG,CU Hand Tie,15kV (F Neck) | EA | 0 |  | 0
Point 16 | XCO-27-100-8-C | Rem | XCO,27kV Polymer,100 Amp,8kA, Corrosive | EA | 0 |  | 0
Point 16 | XFR-50-72-120CUT-1B | Rem | XFR,50KVA,7.2/12.4kVY,120 CUTOVER,1BG | EA | 0 |  | 0
Point 17 | SVC-10-TP-AAA-RS | Tran | SVC,1/0,Trip,All Alum,Res | EA | 1 |  | 0
Point 17 | XFR-25-72-120CUT-1B | Tran | XFR,25KVA,7.2/12.4kVY,120 CUTOVER,1BG | EA | 2 |  | 0
Point 17 | XFR-50-72-120CUT-1B | Tran | XFR,50KVA,7.2/12.4kVY,120 CUTOVER,1BG | EA | 1 |  | 0
Point 18 | BKT-AC183PH-F-C | Rem | BKT,Riser Arr/Term 18in 3Ph,Fbrgls,Corr | EA | 1 |  | 0
Point 18 | BKT-CMX-50-A | Rem | BKT,Cluster Mnt (XFMR),50KVA,Alum | EA | 1 |  | 0
Point 18 | BKT-IP8-F-C | Rem | BKT,Insulator Post 8in,Fbrgls,Corrosive | EA | 1 |  | 0
Point 18 | EQL-3-4-C-40-S-X | Rem | EQL,3 Ph,#4,CU Sol,4/0,CU Str,Xfr | EA | 1 |  | 0
Point 18 | GND-CR-4 | Rem | GND,Cu Clad Rod,#4 | EA | 1 |  | 0
Point 18 | SAA-3-CV-C | Rem | SAA,3 inch,Clevis,Corr | EA | 1 |  | 0
Point 18 | SVD-SG10 | Rem | SVD, Service Grip, 1/0 | EA | 1 |  | 0
Point 18 | XCO-15-100-7 | Rem | XCO,15kVPolymer,100 Amp,7kA | EA | 3 |  | 0
Point 19 | BKT-AC243PH-F-C | Inst | BKT,Riser Arr/Term 24in 3Ph,Fbrgls,Corr | EA | 1 |  | 0
Point 19 | BKT-CMX-167-A | Inst | BKT,Cluster Mnt (XFMR),167KVA,Alum | EA | 1 |  | 0
Point 19 | BKT-IP8-F-C | Inst | BKT,Insulator Post 8in,Fbrgls,Corrosive | EA | 1 |  | 0
Point 19 | CND-HLC2 | Inst | CND,Hot Line clamp #6-#2 | EA | 3 |  | 0
Point 19 | CND-S2O | Inst | CND,Stirrup #2 Open | EA | 3 |  | 0
Point 19 | XCO-27-100-8-C | Inst | XCO,27kV Polymer,100 Amp,8kA, Corrosive | EA | 3 |  | 0
Point 20 | BKT-AC183PH-F-C | Rem | BKT,Riser Arr/Term 18in 3Ph,Fbrgls,Corr | EA | 1 |  | 0
Point 20 | BKT-CMX-167-A | Rem | BKT,Cluster Mnt (XFMR),167KVA,Alum | EA | 1 |  | 0
Point 20 | BKT-IP8-F-C | Rem | BKT,Insulator Post 8in,Fbrgls,Corrosive | EA | 1 |  | 0
Point 20 | EQL-3-4-C-50-S-X | Rem | EQL,3 Ph,#4,CU Sol,500,CU Str,Xfr | EA | 1 |  | 0
Point 20 | GND-CR-4 | Rem | GND,Cu Clad Rod,#4 | EA | 1 |  | 0
Point 20 | SAA-3-CV-C | Rem | SAA,3 inch,Clevis,Corr | EA | 2 |  | 0
Point 20 | XCO-27-100-8-C | Rem | XCO,27kV Polymer,100 Amp,8kA, Corrosive | EA | 3 |  | 0
Point 23 | UGND-TAG-C | Inst | UGND,TAG CABLE MARKER (WHITE),Cable | EA | 0 |  | 0
Point 23 | UPTM-SO-2-15 | Inst | UPTM,Shrink Outdoor,2,15kV | EA | 0 |  | 0
Point 23 | URSG-D-200 | Inst | URSG,Distr,1.75in to 2.00in | EA | 0 |  | 0
Point 23 | URSG-D-CP | Inst | URSG,Distr,Cable Postioner | EA | 0 |  | 0
Point 23 | URSR-3-DSO | Inst | URSR,3in,Dist Stand Off | EA | 0 |  | 0
Point 24 | ARR-10-R | Rem | ARR,10kV,Riser Pole | EA | 0 |  | 0
Point 24 | BKT-AC18-F-C | Rem | BKT,Arrestor/CO 18in (1Ph),Fbrgls,Corr | EA | 0 |  | 0
Point 24 | CND-HLC2 | Rem | CND,Hot Line clamp #6-#2 | EA | 0 |  | 0
Point 24 | CND-S2O | Rem | CND,Stirrup #2 Open | EA | 0 |  | 0
Point 24 | EQL-1-4-C-4-C-E1 | Rem | EQL,1 Phase,#4,Sol,#4,Sol,100a Eq C/O | EA | 0 |  | 0
Point 24 | GND-CR-4 | Rem | GND,Cu Clad Rod,#4 | EA | 1 |  | 0
Point 24 | SAA-3-CV-C | Rem | SAA,3 inch,Clevis,Corr | EA | 0 |  | 0
Point 24 | SWI-27-CO1-100-H-C | Rem | SWI,27kV,Line Cutout 1PH,100A,Hook,C | EA | 0 |  | 0
Point 24 | UGND-TAG-C | Rem | UGND,TAG CABLE MARKER (WHITE),Cable | EA | 0 |  | 0
Point 24 | UPTM-SO-2-15 | Rem | UPTM,Shrink Outdoor,2,15kV | EA | 0 |  | 0
Point 24 | URSG-D-200 | Rem | URSG,Distr,1.75in to 2.00in | EA | 0 |  | 0
Point 24 | URSG-D-CP | Rem | URSG,Distr,Cable Postioner | EA | 0 |  | 0
Point 24 | URSR-3-DSO | Rem | URSR,3in,Dist Stand Off | EA | 0 |  | 0
Point 25 | UGND-TAG-C | Inst | UGND,TAG CABLE MARKER (WHITE),Cable | EA | 0 |  | 0
Point 25 | UPTM-SO-2-15 | Inst | UPTM,Shrink Outdoor,2,15kV | EA | 0 |  | 0
Point 25 | URSG-D-200 | Inst | URSG,Distr,1.75in to 2.00in | EA | 0 |  | 0
Point 25 | URSG-D-CP | Inst | URSG,Distr,Cable Postioner | EA | 0 |  | 0
Point 25 | URSR-3-DSO | Inst | URSR,3in,Dist Stand Off | EA | 0 |  | 0
Point 26 | ARR-10-R | Rem | ARR,10kV,Riser Pole | EA | 0 |  | 0
Point 26 | BKT-AC18-F-C | Rem | BKT,Arrestor/CO 18in (1Ph),Fbrgls,Corr | EA | 0 |  | 0
Point 26 | CND-HLC2 | Rem | CND,Hot Line clamp #6-#2 | EA | 0 |  | 0
Point 26 | CND-S2O | Rem | CND,Stirrup #2 Open | EA | 0 |  | 0
Point 26 | EQL-1-4-C-4-C-E1 | Rem | EQL,1 Phase,#4,Sol,#4,Sol,100a Eq C/O | EA | 0 |  | 0
Point 26 | GND-CR-4 | Rem | GND,Cu Clad Rod,#4 | EA | 0 |  | 0
Point 26 | SWI-27-CO1-100-H-C | Rem | SWI,27kV,Line Cutout 1PH,100A,Hook,C | EA | 0 |  | 0
Point 27 | BKT-CMX-167-A | Inst | BKT,Cluster Mnt (XFMR),167KVA,Alum | EA | 1 |  | 0
Point 27 | XFR-50-72-120CUT-1B-S | Tran | XFR,50KVA,7.2/12.4kVY,120 CUTOVER,1BG,SS | EA | 2 |  | 0
Point 27 | XFR-75-72-120CUT-1B-S | Tran | XFR,75KVA,7.2/12.4kVY,120 CUTOVER,1BG,SS | EA | 1 |  | 0
Point 28 | ANC-DHM-10-84-T1-C | Rem | ANC,Dbl Hlx Mach,10in,84in,TpEye 1in,Cor | EA | 1 |  | 0
Point 28 | ARM-8D-60S | Rem | ARM,8ft Double Wood,60in Sgl.Wd | EA | 1 |  | 0
Point 28 | ARM-BR-60S | Rem | ARM,Brace only Wood,60in Sgl.Wd | EA | 1 |  | 0
Point 28 | BKT-AC183PH-F-C | Rem | BKT,Riser Arr/Term 18in 3Ph,Fbrgls,Corr | EA | 1 |  | 0
Point 28 | BKT-CMX-167-A | Rem | BKT,Cluster Mnt (XFMR),167KVA,Alum | EA | 1 |  | 0
Point 28 | BKT-IP8-F-C | Rem | BKT,Insulator Post 8in,Fbrgls,Corrosive | EA | 1 |  | 0
Point 28 | DEC-20AL-C | Rem | DEC,#4 - #2/0 AA,AL,AS,Corrosive | EA | 3 |  | 0
Point 28 | DEG-40-SPA | Rem | DEG,4/0,Slack Span Alum | EA | 2 |  | 0
Point 28 | EQL-3-4-C-50-S-X | Rem | EQL,3 Ph,#4,CU Sol,500,CU Str,Xfr | EA | 1 |  | 0
Point 28 | GND-CR-4 | Rem | GND,Cu Clad Rod,#4 | EA | 1 |  | 0
Point 28 | GYD-MPY | Rem | GYD,Marker-Plastic-Yellow | EA | 1 |  | 0
Point 28 | GYF-38-42W-I-C | Rem | GYF,3/8,42In Wire Mt,InsulatorAdder,Corr | EA | 1 |  | 0
Point 28 | GYF-38-D-42P-EP-C | Rem | GYF,3/8,Down,42in Pole mt,EyePlate,Corr | EA | 1 |  | 0
Point 28 | GYW-38C | Rem | GYW,3/8 in. Corrosive (16,200 lbs) | FT | 40 |  | 0
Point 28 | INS-15-D-S-C | Rem | INS,15kV,Deadend,Polymer,Corr | EA | 3 |  | 0
Point 28 | INS-15-P-S-C | Rem | INS,15kV,Pin,Silicon Polymer,Corr | EA | 1 |  | 0
Point 28 | PLD-EYE-ARM-C | Rem | PLD, Eyebolt Deadend, Arm,Corrosive | EA | 3 |  | 0
Point 28 | PLD-EYE-C | Rem | PLD,Eyebolt Deadend,Corrosive | EA | 1 |  | 0
Point 28 | POL-45-3 | Rem | Pole,45ft,Class 3 | EA | 0 |  | 0
Point 28 | SAA-3-S3 | Rem | SAA,3 inch,Sec Rack 3 Pos | EA | 1 |  | 0
Point 28 | SAA-DE-20-C | Rem | SAA,DE Clamp #4-2/0, Corr. | EA | 1 |  | 0
Point 28 | TIE-4-CUH-15 | Rem | TIE,4 AWG,CU Hand Tie,15kV (F Neck) | EA | 8 |  | 0
Point 28 | XCO-27-100-8-C | Rem | XCO,27kV Polymer,100 Amp,8kA, Corrosive | EA | 3 |  | 0
Point 28 | XFR-50-72-120CUT-1B-S | Rem | XFR,50KVA,7.2/12.4kVY,120 CUTOVER,1BG,SS | EA | 2 |  | 0
Point 28 | XFR-75-72-120CUT-1B-S | Rem | XFR,75KVA,7.2/12.4kVY,120 CUTOVER,1BG,SS | EA | 1 |  | 0
Point 04 | PLA-CUT | Inst | PLA,Cut Off Pole Top | EA | 1 |  | 0
Point 28 | PLA-CUT | Inst | PLA,Cut Off Pole Top | EA | 1 |  | 0
Point 13 | PLA-DLOC | Inst | PLA,Difficult Location | EA | 2 |  | 0
Point 13 | PLA-BACK | Inst | Difficult Location Equip Adder-Backyard | EA | 11 |  | 0
Point 11 | PLA-DLOC | Inst | PLA,Difficult Location | EA | 2 |  | 0
11 | PLA-BACK | Inst | Difficult Location Equip Adder-Backyard | EA | 11 |  | 0
TOTAL | [6 empty] | 0