## Work Report
WEEKLY UNITS COMPLETED PER SCOPE ID
Report Generated On: 08/18/2025 09:47 PM
| REPORT SUMMARY |  |  |  | REPORT DETAILS
| Total Billed Amount: | 0 |  |  | Foreman: | Jose Mendez
| Total Line Items: | 359 |  |  | Work Request #: | 89719272
| Billing Period: | 07/14/2025 to 07/20/25 |  |  | Scope ID #: | R25P17
[5 empty] | Work Order #: | VARIOUS
[5 empty] | Customer: | AEP
[5 empty] | Job #: | 567-1
Thursday (07/17/2025)
Point Number | Billable Unit Code | Work Type | Unit Description | Unit of Measure | # Units | N/A | Pricing
Point 01 | CNA-TR | Inst | CNA,Transfer Conductor | EA | 1 |  | 0
Point 01 | CNA-TRDE | Inst | CNA Transfer Conductor, Single DE | EA | 1 |  | 0
Point 01 | CON-40-AAA-1-B | Inst | CON,#4/0 AWG,Alum Alloy,One,Bare | FT | 120 |  | 0
Point 01 | DEC-397AL-C | Inst | DEC,#3/0 - #397 AA,AL,AS,Corrosive | EA | 1 |  | 0
Point 01 | GND-CR-4 | Inst | GND,Cu Clad Rod,#4 | EA | 1 |  | 0
Point 01 | GND-LG-SL | Inst | GND,Lug,St Lt | EA | 1 |  | 0
Point 01 | PLD-EYE-C | Inst | PLD,Eyebolt Deadend,Corrosive | EA | 2 |  | 0
Point 01 | SAA-DE-477-C | Inst | SAA, DE Clamp 4/0-477, Corr. | EA | 1 |  | 0
Point 01 | SLB-W-30-A-1-S | Inst | SLB,Wood,30in,Alum,1Pos,Street | EA | 1 |  | 0
Point 01 | SVC-10-TP-AAA-RS | Tran | SVC,1/0,Trip,All Alum,Res | EA | 2 |  | 0
Point 01 | SVD-3-CV-C | Inst | SVD,3 inch,Clevis,Corr | EA | 1 |  | 0
Point 01 | SVD-SG2 | Inst | SVD,Service Grip,#2 | EA | 2 |  | 0
Point 01 | ARM-8SF-GN-TL-C | Inst | ARM,8ft Sgl.Fiberglass,Gain,Tang LD,Corr | EA | 1 |  | 0
Point 01 | BKT-PI18-F | Inst | BKT,Pin insulator 18in,Fbrgls | EA | 2 |  | 0
Point 01 | CNC-SNB-2 | Inst | CNC,Splice Non-Tension Bare,#6-#2 | EA | 2 |  | 0
Point 01 | CNC-SNB-40 | Inst | CNC,Splice Non-Tension Bare,#1/0-#4/0 | EA | 1 |  | 0
Point 01 | CND-HLC10 | Inst | CND,Hot Line Clamp 1/0 | EA | 2 |  | 0
Point 01 | CND-SA477 | Inst | CND,Stirrup,Ampact 477 | EA | 2 |  | 0
Point 01 | EQL-1-4-C-4-C-LC1 | Inst | EQL,1 Phase,#4,Sol,#4,Sol,100a C/O | EA | 2 |  | 0
Point 01 | BKT-AC18-F-C | Inst | BKT,Arrestor/CO 18in (1Ph),Fbrgls,Corr | EA | 1 |  | 0
Point 01 | PIN-15-PTP-C | Inst | Pin,15kV,Pole top,Corrosive | EA | 1 |  | 0
Point 03 | BKT-AC18-F-C | Inst | BKT,Arrestor/CO 18in (1Ph),Fbrgls,Corr | EA | 1 |  | 0
Point 03 | CNA-TR | Inst | CNA,Transfer Conductor | EA | 1 |  | 0
Point 03 | CNA-TRDE | Inst | CNA Transfer Conductor, Single DE | EA | 1 |  | 0
Point 03 | CND-S40795A | Inst | CND,Stirrup 4/0-795 ACSR | EA | 1 |  | 0
Point 03 | CON-40-AAA-1-B | Inst | CON,#4/0 AWG,Alum Alloy,One,Bare | FT | 122 |  | 0
Point 03 | EQL-1-4-C-20-S-X-C | Inst | EQL,1 Ph,#4,CU Sol,2/0,CU Str,Xfr,Corr | EA | 1 |  | 0
Point 03 | GND-CR-4 | Inst | GND,Cu Clad Rod,#4 | EA | 1 |  | 0
Point 03 | PIN-15-PTP-C | Inst | Pin,15kV,Pole top,Corrosive | EA | 1 |  | 0
Point 03 | SAA-3-CV-C | Inst | SAA,3 inch,Clevis,Corr | EA | 1 |  | 0
Point 03 | SVC-10-TP-AAA-RS | Tran | SVC,1/0,Trip,All Alum,Res | EA | 2 |  | 0
Point 03 | SVD-SG2 | Inst | SVD,Service Grip,#2 | EA | 2 |  | 0
Point 03 | TIE-4-ALH-F | Inst | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 03 | XCO-27-100-8-C | Inst | XCO,27kV Polymer,100 Amp,8kA, Corrosive | EA | 1 |  | 0
Point 03 | XFR-50-72-120-1B-S | Tran | XFR,50KVA,7.2/12.4kVY,120/240,1BG,SS | EA | 1 |  | 0
Point 05 | CNA-TR | Inst | CNA,Transfer Conductor | EA | 1 |  | 0
Point 05 | CNA-TRDE | Inst | CNA Transfer Conductor, Single DE | EA | 1 |  | 0
Point 05 | CON-40-AAA-1-B | Inst | CON,#4/0 AWG,Alum Alloy,One,Bare | FT | 120 |  | 0
Point 05 | INS-15-P-S-C | Inst | INS,15kV,Pin,Silicon Polymer,Corr | EA | 1 |  | 0
Point 05 | PIN-15-PTP-C | Inst | Pin,15kV,Pole top,Corrosive | EA | 1 |  | 0
Point 05 | SAA-3-CV-C | Inst | SAA,3 inch,Clevis,Corr | EA | 1 |  | 0
Point 05 | SVC-10-TP-AAA-RS | Tran | SVC,1/0,Trip,All Alum,Res | EA | 2 |  | 0
Point 05 | SVD-3-CV-C | Inst | SVD,3 inch,Clevis,Corr | EA | 1 |  | 0
Point 05 | SVD-SG2 | Inst | SVD,Service Grip,#2 | EA | 2 |  | 0
Point 05 | TIE-4-ALH-F | Inst | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 05 | BKT-AC18-F-C | Inst | BKT,Arrestor/CO 18in (1Ph),Fbrgls,Corr | EA | 2 |  | 0
Point 05 | CND-S620A | Inst | CND,Stirrup #6-2/0 AL or ACSR | EA | 1 |  | 0
Point 07 | BKT-AC18-F-C | Inst | BKT,Arrestor/CO 18in (1Ph),Fbrgls,Corr | EA | 1 |  | 0
Point 07 | CNA-TR | Inst | CNA,Transfer Conductor | EA | 1 |  | 0
Point 07 | CNA-TRDE | Inst | CNA Transfer Conductor, Single DE | EA | 1 |  | 0
Point 07 | CND-HLC2 | Inst | CND,Hot Line clamp #6-#2 | EA | 1 |  | 0
Point 07 | CND-S40795A | Inst | CND,Stirrup 4/0-795 ACSR | EA | 1 |  | 0
Point 07 | CON-40-AAA-1-B | Inst | CON,#4/0 AWG,Alum Alloy,One,Bare | FT | 121 |  | 0
Point 07 | EQL-1-4-C-20-S-X-C | Inst | EQL,1 Ph,#4,CU Sol,2/0,CU Str,Xfr,Corr | EA | 1 |  | 0
Point 07 | GND-CR-4 | Inst | GND,Cu Clad Rod,#4 | EA | 1 |  | 0
Point 07 | SAA-SP-336 | Inst | SAA,Spreader Bkt, 336MCM Max | EA | 3 |  | 0
Point 07 | SLT-LED-RW-T3-14L-SF | Inst | 14kL LED, Type 3, Roadway | EA | 1 |  | 0
Point 07 | SVC-10-TP-AAA-RS | Tran | SVC,1/0,Trip,All Alum,Res | EA | 2 |  | 0
Point 07 | SVD-3-CV-C | Inst | SVD,3 inch,Clevis,Corr | EA | 1 |  | 0
Point 07 | SVD-SG2 | Inst | SVD,Service Grip,#2 | EA | 2 |  | 0
Point 07 | TIE-4-ALH-F | Inst | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 07 | XCO-27-100-8-C | Inst | XCO,27kV Polymer,100 Amp,8kA, Corrosive | EA | 1 |  | 0
Point 07 | TIE-4-ALH-F | Inst | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 09 | CNA-TR | Inst | CNA,Transfer Conductor | EA | 1 |  | 0
Point 09 | CNA-TRDE | Inst | CNA Transfer Conductor, Single DE | EA | 1 |  | 0
Point 09 | CON-40-AAA-1-B | Inst | CON,#4/0 AWG,Alum Alloy,One,Bare | FT | 120 |  | 0
Point 09 | SVC-10-TP-AAA-RS | Tran | SVC,1/0,Trip,All Alum,Res | EA | 2 |  | 0
Point 09 | SVD-3-CV-C | Inst | SVD,3 inch,Clevis,Corr | EA | 1 |  | 0
Point 09 | SVD-SG2 | Inst | SVD,Service Grip,#2 | EA | 2 |  | 0
Point 09 | TIE-4-ALH-F | Inst | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 11 | CNA-TR | Inst | CNA,Transfer Conductor | EA | 1 |  | 0
Point 11 | CNA-TRDE | Inst | CNA Transfer Conductor, Single DE | EA | 1 |  | 0
Point 11 | CND-HLC2 | Inst | CND,Hot Line clamp #6-#2 | EA | 1 |  | 0
Point 11 | CND-S40795A | Inst | CND,Stirrup 4/0-795 ACSR | EA | 1 |  | 0
Point 11 | CON-40-AAA-1-B | Inst | CON,#4/0 AWG,Alum Alloy,One,Bare | FT | 120 |  | 0
Point 11 | EQL-1-4-C-20-S-X-C | Inst | EQL,1 Ph,#4,CU Sol,2/0,CU Str,Xfr,Corr | EA | 1 |  | 0
Point 11 | GND-CR-4 | Inst | GND,Cu Clad Rod,#4 | EA | 1 |  | 0
Point 11 | SAA-3-CV-C | Inst | SAA,3 inch,Clevis,Corr | EA | 1 |  | 0
Point 11 | SAA-SP-336 | Inst | SAA,Spreader Bkt, 336MCM Max | EA | 1 |  | 0
Point 11 | SVC-10-TP-AAA-RS | Tran | SVC,1/0,Trip,All Alum,Res | EA | 2 |  | 0
Point 11 | SVD-3-CV-C | Inst | SVD,3 inch,Clevis,Corr | EA | 1 |  | 0
Point 11 | SVD-SG2 | Inst | SVD,Service Grip,#2 | EA | 2 |  | 0
Point 11 | TIE-4-ALH-F | Inst | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 11 | XCO-27-100-8-C | Inst | XCO,27kV Polymer,100 Amp,8kA, Corrosive | EA | 1 |  | 0
Point 11 | XFR-75-72-120-1B-S | Tran | XFR,75KVA,7.2/12.4kVY,120/240,1BG,SS | EA | 1 |  | 0
Point 15 | CON-10-AAA-1-B-REEL | Inst | CON,#1/0 AWG,Alum Alloy,One,Bare,Reel | FT | 75 |  | 0
Point 15 | CON-40-AAA-1-B | Inst | CON,#4/0 AWG,Alum Alloy,One,Bare | FT | 75 |  | 0
Point 15 | DEC-397AL-C | Inst | DEC,#3/0 - #397 AA,AL,AS,Corrosive | EA | 2 |  | 0
Point 15 | INS-15-D-S-C | Inst | INS,15kV,Deadend,Polymer,Corr | EA | 1 |  | 0
Point 15 | SLT-LED-RW-T3-14L-SF | Inst | 14kL LED, Type 3, Roadway | EA | 1 |  | 0
TOTAL | [6 empty] | 0
Friday (07/18/2025)
Point Number | Billable Unit Code | Work Type | Unit Description | Unit of Measure | # Units | N/A | Pricing
Point 01 | GND-MD | Inst | GND,Wire Mldg Only | EA | 2 |  | 0
Point 01 | ARM-8SF-GN-TL | Inst | ARM,8ft Sgl.Fiberglass,Gain,Tangent LD | EA | 0 |  | 0
Point 01 | TIE-4-ALH-F | Inst | TIE,4 AWG,AL Hand Tie,F Neck | EA | 6 |  | 0
Point 01 | CND-HLC2 | Inst | CND,Hot Line clamp #6-#2 | EA | 1 |  | 0
Point 01 | GYF-38-D-78P-EP-C | Inst | GYF,3/8,Down,78in Pole mt,EyePlate,Corr | EA | 1 |  | 0
Point 01 | SAA-3-CV-C | Inst | SAA,3 inch,Clevis,Corr | EA | 2 |  | 0
Point 02 | GYF-38-78W-I-C | Rem | GYF,3/8,78Wire mt,Insulator Adder,Corros | EA | 0 |  | 0
Point 02 | GYF-38-D-42P-EP-C | Rem | GYF,3/8,Down,42in Pole mt,EyePlate,Corr | EA | 0 |  | 0
Point 02 | CON-2-AAA-1-B-REEL | Rem | CON,#2 AWG,Alum Alloy,One,Bare,Reels | FT | 122 |  | 0
Point 02 | GND-MD | Rem | GND,Wire Mldg Only | EA | 1 |  | 0
Point 04 | CON-2-AAA-1-B-REEL | Rem | CON,#2 AWG,Alum Alloy,One,Bare,Reels | FT | 120 |  | 0
Point 04 | GND-CR-4 | Rem | GND,Cu Clad Rod,#4 | EA | 0 |  | 0
Point 04 | GND-CR-4 | Rem | GND,Cu Clad Rod,#4 | EA | 1 |  | 0
Point 04 | GND-MD | Rem | GND,Wire Mldg Only | EA | 1 |  | 0
Point 05 | POL-45-2 | Inst | Pole,45ft,Class 2 | EA | 0 |  | 0
Point 05 | GND-CR-4 | Inst | GND,Cu Clad Rod,#4 | EA | 0 |  | 0
Point 05 | GND-MD | Inst | GND,Wire Mldg Only | EA | 0 |  | 0
Point 05 | TIE-4-ALH-F | Inst | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 06 | CON-2-AAA-1-B-REEL | Rem | CON,#2 AWG,Alum Alloy,One,Bare,Reels | FT | 122 |  | 0
Point 06 | POL-40-4 | Rem | Pole,40ft,Class 4 | EA | 0 |  | 0
Point 08 | CON-2-AAA-1-B-REEL | Rem | CON,#2 AWG,Alum Alloy,One,Bare,Reels | FT | 121 |  | 0
Point 08 | GND-MD | Rem | GND,Wire Mldg Only | EA | 1 |  | 0
Point 08 | POL-40-5 | Rem | Pole,40ft,Class 5 | EA | 0 |  | 0
Point 10 | CON-2-AAA-1-B-REEL | Rem | CON,#2 AWG,Alum Alloy,One,Bare,Reels | FT | 120 |  | 0
Point 10 | GND-CR-4 | Rem | GND,Cu Clad Rod,#4 | EA | 1 |  | 0
Point 10 | GND-MD | Rem | GND,Wire Mldg Only | EA | 1 |  | 0
Point 10 | TIE-4-ALH-F | Rem | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 12 | GND-CR-4 | Rem | GND,Cu Clad Rod,#4 | EA | 1 |  | 0
Point 12 | GND-MD | Rem | GND,Wire Mldg Only | EA | 1 |  | 0
Point 12 | TIE-4-ALH-F | Rem | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 13 | CON-40-AAA-1-B | Inst | CON,#4/0 AWG,Alum Alloy,One,Bare | FT | 81 |  | 0
Point 13 | TIE-4-ALH-F | Inst | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 14 | CON-2-AAA-1-B-REEL | Rem | CON,#2 AWG,Alum Alloy,One,Bare,Reels | FT | 100 |  | 0
Point 14 | GND-CR-4 | Rem | GND,Cu Clad Rod,#4 | EA | 1 |  | 0
Point 14 | GND-MD | Rem | GND,Wire Mldg Only | EA | 1 |  | 0
Point 14 | PIN-15-PTP-C | Rem | Pin,15kV,Pole top,Corrosive | EA | 1 |  | 0
Point 17 | GND-CR-4 | Inst | GND,Cu Clad Rod,#4 | EA | 1 |  | 0
Point 17 | GND-MD | Inst | GND,Wire Mldg Only | EA | 2 |  | 0
Point 17 | BKT-AC18-F-C | Inst | BKT,Arrestor/CO 18in (1Ph),Fbrgls,Corr | EA | 0 |  | 0
Point 17 | TIE-4-ALH-F | Inst | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 18 | EQL-3-4-C-2-S-X | Rem | EQL,3 Ph,#4,CU Sol,#2,CU Str,Xfr | EA | 1 |  | 0
Point 18 | GND-CR-4 | Rem | GND,Cu Clad Rod,#4 | EA | 1 |  | 0
Point 18 | GND-MD | Rem | GND,Wire Mldg Only | EA | 1 |  | 0
Point 18 | GYF-38-78W-I-C | Rem | GYF,3/8,78Wire mt,Insulator Adder,Corros | EA | 2 |  | 0
Point 18 | GYF-38-D-42P-EP-C | Rem | GYF,3/8,Down,42in Pole mt,EyePlate,Corr | EA | 2 |  | 0
Point 18 | TIE-4-ALH-F | Rem | TIE,4 AWG,AL Hand Tie,F Neck | EA | 6 |  | 0
Point 18 | CND-HLC2 | Rem | CND,Hot Line clamp #6-#2 | EA | 1 |  | 0
Point 18 | XCO-27-100-8-C | Rem | XCO,27kV Polymer,100 Amp,8kA, Corrosive | EA | 1 |  | 0
Point 18 | XFR-50-72-120-2B-S | Rem | XFR,50KVA,7.2/12.4kVY,120/240,2BG,SS | EA | 1 |  | 0
Point 18 | BKT-AC18-F-C | Rem | BKT,Arrestor/CO 18in (1Ph),Fbrgls,Corr | EA | 1 |  | 0
Point 18 | EQL-1-4-C-2-S-X-C | Rem | EQL,1 Ph,#4,CU Sol,#2,CU Str,Xfr,Corr | EA | 1 |  | 0
Point 18 | PLA-CUT | Rem | PLA,Cut Off Pole Top | EA | 1 |  | 0
Point 18 | TIE-4-ALH-F | Rem | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 18 | XCO-15-100-7 | Rem | XCO,15kVPolymer,100 Amp,7kA | EA | 1 |  | 0
Point 18 | PIN-15-PTP-C | Rem | Pin,15kV,Pole top,Corrosive | EA | 1 |  | 0
Point 18 | POL-40-5 | Rem | Pole,40ft,Class 5 | EA | 0 |  | 0
Point 19 | BKT-AC18-F-C | Inst | BKT,Arrestor/CO 18in (1Ph),Fbrgls,Corr | EA | 2 |  | 0
Point 19 | CNA-TR | Inst | CNA,Transfer Conductor | EA | 4 |  | 0
Point 19 | CNA-TRDE | Inst | CNA Transfer Conductor, Single DE | EA | 4 |  | 0
Point 19 | CND-HLC2 | Inst | CND,Hot Line clamp #6-#2 | EA | 2 |  | 0
Point 19 | GND-CR-4 | Inst | GND,Cu Clad Rod,#4 | EA | 1 |  | 0
Point 20 | INS-15-P-S-C | Rem | INS,15kV,Pin,Silicon Polymer,Corr | EA | 3 |  | 0
Point 20 | POL-40-2 | Rem | Pole,40ft,Class 2 | EA | 0 |  | 0
Point 20 | BKT-AC18-F-C | Rem | BKT,Arrestor/CO 18in (1Ph),Fbrgls,Corr | EA | 2 |  | 0
Point 20 | POL-45-4 | Rem | Pole,45ft,Class 4 | EA | 0 |  | 0
Point 20 | POL-40-4 | Rem | Pole,40ft,Class 4 | EA | 0 |  | 0
Point 20 | TIE-4-ALH-F | Rem | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 22 | PIN-15-PTP-C | Rem | Pin,15kV,Pole top,Corrosive | EA | 1 |  | 0
Point 22 | POL-40-5 | Rem | Pole,40ft,Class 5 | EA | 1 |  | 0
Point 22 | TIE-4-ALH-F | Rem | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 22 | GND-CR-4 | Rem | GND,Cu Clad Rod,#4 | EA | 1 |  | 0
Point 22 | GND-MD | Rem | GND,Wire Mldg Only | EA | 1 |  | 0
Point 22 | PLA-CUT | Rem | PLA,Cut Off Pole Top | EA | 1 |  | 0
Point 22 | POL-40-4 | Rem | Pole,40ft,Class 4 | EA | 0 |  | 0
Point 22 | TIE-4-ALH-F | Rem | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 24 | TIE-4-ALH-F | Rem | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 24 | PIN-15-PTP-C | Rem | Pin,15kV,Pole top,Corrosive | EA | 1 |  | 0
Point 24 | POL-40-4 | Rem | Pole,40ft,Class 4 | EA | 0 |  | 0
Point 25 | XFR-25-72-120-1B-S | Tran | XFR,25KVA,7.2/12.4kVY,120/240,1BG,SS | EA | 1 |  | 0
Point 26 | CND-HLC2 | Rem | CND,Hot Line clamp #6-#2 | EA | 1 |  | 0
Point 26 | PIN-15-PTP-C | Rem | Pin,15kV,Pole top,Corrosive | EA | 1 |  | 0
Point 26 | POL-40-5 | Rem | Pole,40ft,Class 5 | EA | 0 |  | 0
Point 26 | TIE-4-ALH-F | Rem | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 26 | CND-HLC2 | Rem | CND,Hot Line clamp #6-#2 | EA | 1 |  | 0
Point 26 | PIN-15-PTP-C | Rem | Pin,15kV,Pole top,Corrosive | EA | 1 |  | 0
Point 26 | POL-40-4 | Rem | Pole,40ft,Class 4 | EA | 0 |  | 0
Point 26 | GND-MD | Rem | GND,Wire Mldg Only | EA | 1 |  | 0
Point 26 | POL-40-4 | Rem | Pole,40ft,Class 4 | EA | 0 |  | 0
Point 26 | XCO-15-100-7 | Rem | XCO,15kVPolymer,100 Amp,7kA | EA | 1 |  | 0
Point 27 | CNA-TR | Inst | CNA,Transfer Conductor | EA | 2 |  | 0
Point 27 | CNA-TRDE | Inst | CNA Transfer Conductor, Single DE | EA | 1 |  | 0
Point 27 | GND-MD | Inst | GND,Wire Mldg Only | EA | 2 |  | 0
Point 27 | TIE-4-ALH-F | Inst | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 28 | GND-CR-4 | Rem | GND,Cu Clad Rod,#4 | EA | 1 |  | 0
Point 28 | GND-MD | Rem | GND,Wire Mldg Only | EA | 1 |  | 0
Point 28 | PIN-15-PTP-C | Rem | Pin,15kV,Pole top,Corrosive | EA | 1 |  | 0
Point 28 | PLD-EYE-C | Rem | PLD,Eyebolt Deadend,Corrosive | EA | 1 |  | 0
Point 28 | POL-40-4 | Rem | Pole,40ft,Class 4 | EA | 0 |  | 0
Point 28 | TIE-4-ALH-F | Rem | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 28 | PIN-15-PTP-C | Rem | Pin,15kV,Pole top,Corrosive | EA | 1 |  | 0
Point 28 | POL-40-4 | Rem | Pole,40ft,Class 4 | EA | 0 |  | 0
Point 28 | TIE-4-ALH-F | Rem | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 29 | BKT-AC18-F-C | Inst | BKT,Arrestor/CO 18in (1Ph),Fbrgls,Corr | EA | 1 |  | 0
Point 29 | CNA-TR | Inst | CNA,Transfer Conductor | EA | 2 |  | 0
Point 29 | CNA-TRDE | Inst | CNA Transfer Conductor, Single DE | EA | 1 |  | 0
Point 29 | CND-HLC2 | Inst | CND,Hot Line clamp #6-#2 | EA | 1 |  | 0
Point 29 | EQL-1-4-C-2-S-X-C | Inst | EQL,1 Ph,#4,CU Sol,#2,CU Str,Xfr,Corr | EA | 1 |  | 0
Point 29 | SVC-10-TP-AAA-RS | Tran | SVC,1/0,Trip,All Alum,Res | EA | 1 |  | 0
Point 29 | SVC-VA | Inst | SVC-Virtual Asset Capitalization | EA | 0 |  | 0
Point 29 | SVD-3-CV-C | Inst | SVD,3 inch,Clevis,Corr | EA | 1 |  | 0
Point 29 | SVD-SG2 | Inst | SVD,Service Grip,#2 | EA | 1 |  | 0
Point 29 | TIE-4-ALH-F | Inst | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 29 | XCO-27-100-8-C | Inst | XCO,27kV Polymer,100 Amp,8kA, Corrosive | EA | 1 |  | 0
Point 29 | XFR-25-72-120-1B-S | Inst | XFR,25KVA,7.2/12.4kVY,120/240,1BG,SS | EA | 1 |  | 0
Point 30 | BKT-AC18-F-C | Rem | BKT,Arrestor/CO 18in (1Ph),Fbrgls,Corr | EA | 1 |  | 0
Point 30 | CND-HLC2 | Rem | CND,Hot Line clamp #6-#2 | EA | 1 |  | 0
Point 30 | CND-S620A | Rem | CND,Stirrup #6-2/0 AL or ACSR | EA | 1 |  | 0
Point 30 | EQL-1-4-C-2-S-X-C | Rem | EQL,1 Ph,#4,CU Sol,#2,CU Str,Xfr,Corr | EA | 1 |  | 0
Point 30 | GND-CR-4 | Rem | GND,Cu Clad Rod,#4 | EA | 1 |  | 0
Point 30 | GND-MD | Rem | GND,Wire Mldg Only | EA | 1 |  | 0
Point 30 | PIN-15-PTP-C | Rem | Pin,15kV,Pole top,Corrosive | EA | 1 |  | 0
Point 30 | PLD-EYE-C | Rem | PLD,Eyebolt Deadend,Corrosive | EA | 1 |  | 0
Point 30 | POL-40-4 | Rem | Pole,40ft,Class 4 | EA | 0 |  | 0
Point 30 | SAA-3-CV-C | Rem | SAA,3 inch,Clevis,Corr | EA | 1 |  | 0
Point 30 | TIE-4-ALH-F | Rem | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 30 | XCO-27-100-8-C | Rem | XCO,27kV Polymer,100 Amp,8kA, Corrosive | EA | 1 |  | 0
Point 30 | XFR-25-72-120-1B-S | Rem | XFR,25KVA,7.2/12.4kVY,120/240,1BG,SS | EA | 1 |  | 0
Point 30 | GND-MD | Rem | GND,Wire Mldg Only | EA | 1 |  | 0
Point 30 | PIN-15-PTP-C | Rem | Pin,15kV,Pole top,Corrosive | EA | 0 |  | 0
Point 30 | POL-40-4 | Rem | Pole,40ft,Class 4 | EA | 0 |  | 0
Point 30 | SAA-3-CV-C | Rem | SAA,3 inch,Clevis,Corr | EA | 0 |  | 0
Point 30 | TIE-4-ALH-F | Rem | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 30 | BKT-AC18-F-C | Rem | BKT,Arrestor/CO 18in (1Ph),Fbrgls,Corr | EA | 0 |  | 0
Point 30 | CND-HLC2 | Rem | CND,Hot Line clamp #6-#2 | EA | 1 |  | 0
Point 30 | EQL-1-4-C-2-S-X-C | Rem | EQL,1 Ph,#4,CU Sol,#2,CU Str,Xfr,Corr | EA | 0 |  | 0
Point 30 | GND-CR-4 | Rem | GND,Cu Clad Rod,#4 | EA | 1 |  | 0
Point 30 | GND-MD | Rem | GND,Wire Mldg Only | EA | 0 |  | 0
Point 30 | PIN-15-PTP-C | Rem | Pin,15kV,Pole top,Corrosive | EA | 1 |  | 0
Point 30 | PLA-CUT | Rem | PLA,Cut Off Pole Top | EA | 1 |  | 0
Point 30 | POL-40-4 | Rem | Pole,40ft,Class 4 | EA | 0 |  | 0
Point 30 | SAA-3-CV-C | Rem | SAA,3 inch,Clevis,Corr | EA | 1 |  | 0
Point 30 | TIE-4-ALH-F | Rem | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 30 | XCO-15-100-7 | Rem | XCO,15kVPolymer,100 Amp,7kA | EA | 1 |  | 0
Point 31 | BKT-AC18-F-C | Inst | BKT,Arrestor/CO 18in (1Ph),Fbrgls,Corr | EA | 1 |  | 0
Point 31 | CNA-TR | Inst | CNA,Transfer Conductor | EA | 3 |  | 0
Point 31 | CNA-TRDE | Inst | CNA Transfer Conductor, Single DE | EA | 1 |  | 0
Point 31 | CND-HLC2 | Inst | CND,Hot Line clamp #6-#2 | EA | 1 |  | 0
Point 31 | CND-S40795A | Inst | CND,Stirrup 4/0-795 ACSR | EA | 1 |  | 0
Point 31 | EQL-1-4-C-2-S-X-C | Inst | EQL,1 Ph,#4,CU Sol,#2,CU Str,Xfr,Corr | EA | 1 |  | 0
Point 31 | SVC-10-TP-AAA-RS | Tran | SVC,1/0,Trip,All Alum,Res | EA | 1 |  | 0
Point 31 | SVC-VA | Inst | SVC-Virtual Asset Capitalization | EA | 0 |  | 0
Point 31 | SVD-3-CV-C | Inst | SVD,3 inch,Clevis,Corr | EA | 2 |  | 0
Point 31 | SVD-SG2 | Inst | SVD,Service Grip,#2 | EA | 3 |  | 0
Point 31 | TIE-4-ALH-F | Inst | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 31 | XCO-27-100-8-C | Inst | XCO,27kV Polymer,100 Amp,8kA, Corrosive | EA | 1 |  | 0
Point 31 | XFR-25-72-120-1B-S | Tran | XFR,25KVA,7.2/12.4kVY,120/240,1BG,SS | EA | 1 |  | 0
Point 32 | BKT-AC18-F-C | Rem | BKT,Arrestor/CO 18in (1Ph),Fbrgls,Corr | EA | 1 |  | 0
Point 32 | CND-HLC2 | Rem | CND,Hot Line clamp #6-#2 | EA | 1 |  | 0
Point 32 | CND-S620A | Rem | CND,Stirrup #6-2/0 AL or ACSR | EA | 1 |  | 0
Point 32 | EQL-1-4-C-2-S-X-C | Rem | EQL,1 Ph,#4,CU Sol,#2,CU Str,Xfr,Corr | EA | 1 |  | 0
Point 32 | GND-CR-4 | Rem | GND,Cu Clad Rod,#4 | EA | 1 |  | 0
Point 32 | GND-MD | Rem | GND,Wire Mldg Only | EA | 1 |  | 0
Point 32 | PIN-15-PTP-C | Rem | Pin,15kV,Pole top,Corrosive | EA | 0 |  | 0
Point 32 | POL-40-4 | Rem | Pole,40ft,Class 4 | EA | 0 |  | 0
Point 32 | TIE-4-ALH-F | Rem | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 32 | XCO-27-100-8-C | Rem | XCO,27kV Polymer,100 Amp,8kA, Corrosive | EA | 1 |  | 0
Point 32 | TIE-4-ALH-F | Rem | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 32 | PIN-15-PTP-C | Rem | Pin,15kV,Pole top,Corrosive | EA | 0 |  | 0
Point 32 | POL-40-4 | Rem | Pole,40ft,Class 4 | EA | 0 |  | 0
Point 32 | TIE-4-ALH-F | Rem | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 33 | BKT-AC18-F-C | Inst | BKT,Arrestor/CO 18in (1Ph),Fbrgls,Corr | EA | 1 |  | 0
Point 33 | CNA-TR | Inst | CNA,Transfer Conductor | EA | 2 |  | 0
Point 33 | CNA-TRDE | Inst | CNA Transfer Conductor, Single DE | EA | 1 |  | 0
Point 33 | CND-HLC2 | Inst | CND,Hot Line clamp #6-#2 | EA | 1 |  | 0
Point 33 | EQL-1-4-C-2-S-X-C | Inst | EQL,1 Ph,#4,CU Sol,#2,CU Str,Xfr,Corr | EA | 1 |  | 0
Point 33 | GND-CR-4 | Inst | GND,Cu Clad Rod,#4 | EA | 1 |  | 0
Point 33 | GND-MD | Inst | GND,Wire Mldg Only | EA | 2 |  | 0
Point 33 | TIE-4-ALH-F | Inst | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 33 | XCO-27-100-8-C | Inst | XCO,27kV Polymer,100 Amp,8kA, Corrosive | EA | 1 |  | 0
Point 33 | XFR-25-72-120-1B-S | Tran | XFR,25KVA,7.2/12.4kVY,120/240,1BG,SS | EA | 1 |  | 0
Point 34 | BKT-AC18-F-C | Rem | BKT,Arrestor/CO 18in (1Ph),Fbrgls,Corr | EA | 1 |  | 0
Point 34 | CND-HLC2 | Rem | CND,Hot Line clamp #6-#2 | EA | 1 |  | 0
Point 34 | EQL-1-4-C-2-S-X-C | Rem | EQL,1 Ph,#4,CU Sol,#2,CU Str,Xfr,Corr | EA | 1 |  | 0
Point 34 | GND-CR-4 | Rem | GND,Cu Clad Rod,#4 | EA | 1 |  | 0
Point 34 | GND-MD | Rem | GND,Wire Mldg Only | EA | 1 |  | 0
Point 34 | PIN-15-PTP-C | Rem | Pin,15kV,Pole top,Corrosive | EA | 0 |  | 0
Point 34 | POL-40-4 | Rem | Pole,40ft,Class 4 | EA | 0 |  | 0
Point 34 | TIE-4-ALH-F | Rem | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 34 | XCO-27-100-8-C | Rem | XCO,27kV Polymer,100 Amp,8kA, Corrosive | EA | 1 |  | 0
Point 34 | TIE-4-ALH-F | Rem | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 34 | PIN-15-PTP-C | Rem | Pin,15kV,Pole top,Corrosive | EA | 1 |  | 0
Point 34 | POL-40-4 | Rem | Pole,40ft,Class 4 | EA | 0 |  | 0
Point 34 | TIE-4-ALH-F | Rem | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 35 | CNA-TR | Inst | CNA,Transfer Conductor | EA | 1 |  | 0
Point 35 | CNA-TRDE | Inst | CNA Transfer Conductor, Single DE | EA | 1 |  | 0
Point 35 | GND-MD | Inst | GND,Wire Mldg Only | EA | 2 |  | 0
Point 35 | GYW-38C | Inst | GYW,3/8 in. Corrosive (16,200 lbs) | FT | 40 |  | 0
Point 35 | INS-15-P-S-C | Inst | INS,15kV,Pin,Silicon Polymer,Corr | EA | 0 |  | 0
Point 35 | PIN-15-PTP-C | Inst | Pin,15kV,Pole top,Corrosive | EA | 0 |  | 0
Point 35 | TIE-4-ALH-F | Inst | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 35 | XCO-27-100-8-C | Inst | XCO,27kV Polymer,100 Amp,8kA, Corrosive | EA | 1 |  | 0
Point 35 | TIE-4-ALH-F | Inst | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 36 | ANC-DHM-8-84-T1-C | Rem | ANC,Dbl Hlx Mach,8in,84in,TpEye 1in,Cor | EA | 0 |  | 0
Point 36 | XFR-50-72-120-1B-S | Rem | XFR,50KVA,7.2/12.4kVY,120/240,1BG,SS | EA | 1 |  | 0
Point 36 | TIE-4-ALH-F | Rem | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 36 | POL-40-4 | Rem | Pole,40ft,Class 4 | EA | 0 |  | 0
Point 36 | TIE-4-ALH-F | Rem | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 25 | CNA-TR | Inst | CNA,Transfer Conductor | EA | 2 |  | 0
Point 25 | CNA-TRDE | Inst | CNA Transfer Conductor, Single DE | EA | 2 |  | 0
Point 25 | EQL-1-4-C-2-S-X-C | Inst | EQL,1 Ph,#4,CU Sol,#2,CU Str,Xfr,Corr | EA | 1 |  | 0
Point 25 | SVD-3-CV-C | Inst | SVD,3 inch,Clevis,Corr | EA | 1 |  | 0
Point 25 | TIE-4-ALH-F | Inst | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 25 | XCO-27-100-8-C | Inst | XCO,27kV Polymer,100 Amp,8kA, Corrosive | EA | 1 |  | 0
Point 25 | GND-CR-4 | Inst | GND,Cu Clad Rod,#4 | EA | 1 |  | 0
Point 25 | GND-MD | Inst | GND,Wire Mldg Only | EA | 2 |  | 0
Point 25 | PIN-15-PTP-C | Inst | Pin,15kV,Pole top,Corrosive | EA | 1 |  | 0
Point 03 | DEG-10-PSC-15 | Rem | DEG, 1/0, Pri.Spacer Cable, 15KV | EA | 1 |  | 0
Point 01 | PLA-CUT | Inst | PLA,Cut Off Pole Top | EA | 0 |  | 0
Point 03 | PLA-CUT | Inst | PLA,Cut Off Pole Top | EA | 0 |  | 0
Point 3 | PLA-CUT | Inst | PLA,Cut Off Pole Top | EA | 1 |  | 0
Point 01 | CNC-SNI-40 | Inst | CNC,Svc.spl. Non-Tension insul,#1/0-#4/0 | EA | 0 |  | 0
Point 01 | CNC-SNI-40 | Inst | CNC,Svc.spl. Non-Tension insul,#1/0-#4/0 | EA | 4 |  | 0
Point 01 | CNC-SNB-2 | Inst | CNC,Splice Non-Tension Bare,#6-#2 | EA | 2 |  | 0
Point 01 | GYF-38-78W-I-C | Inst | GYF,3/8,78Wire mt,Insulator Adder,Corros | EA | 1 |  | 0
Point 03 | CNC-SNI-40 | Inst | CNC,Svc.spl. Non-Tension insul,#1/0-#4/0 | EA | 7 |  | 0
Point 03 | CNC-SNB-2 | Inst | CNC,Splice Non-Tension Bare,#6-#2 | EA | 4 |  | 0
Point 03 | PLA-CUT | Inst | #NO MATCH | #NO MATCH | 1 |  | 0
Point 3 | CNC-HDA | Inst | #NO MATCH | #NO MATCH | 0 |  | 0
Point 04 | PLA-CUT | Inst | PLA,Cut Off Pole Top | EA | 1 |  | 0
Point 05 | CNC-NTS-2 | Inst | CNC, Non-Tension Splice for Serv,#6-#2 | EA | 3 |  | 0
Point 05 | CNC-SNB-2 | Inst | CNC,Splice Non-Tension Bare,#6-#2 | EA | 2 |  | 0
Point 05 | CNC-SNB-40 | Inst | CNC,Splice Non-Tension Bare,#1/0-#4/0 | EA | 4 |  | 0
Point 6 | PLA-CUT | Inst | PLA,Cut Off Pole Top | EA | 1 |  | 0
Point 07 | CNC-SNB-2 | Inst | CNC,Splice Non-Tension Bare,#6-#2 | EA | 6 |  | 0
Point 07 | CNC-SNI-40 | Inst | CNC,Svc.spl. Non-Tension insul,#1/0-#4/0 | EA | 3 |  | 0
Point 08 | PLA-CUT | Inst | PLA,Cut Off Pole Top | EA | 1 |  | 0
Point 09 | CNC-SNI-40 | Inst | CNC,Svc.spl. Non-Tension insul,#1/0-#4/0 | EA | 4 |  | 0
Point 09 | CNC-SNB-2 | Inst | CNC,Splice Non-Tension Bare,#6-#2 | EA | 4 |  | 0
Point 10 | PLA-CUT | Inst | #NO MATCH | #NO MATCH | 0 |  | 0
Point 11 | CNC-SNI-40 | Inst | CNC,Svc.spl. Non-Tension insul,#1/0-#4/0 | EA | 4 |  | 0
Point 11 | CNC-NTS-2 | Inst | CNC, Non-Tension Splice for Serv,#6-#2 | EA | 2 |  | 0
Point 12 | PLA-CUT | Inst | PLA,Cut Off Pole Top | EA | 1 |  | 0
Point 13 | CNC-SNI-40 | Inst | CNC,Svc.spl. Non-Tension insul,#1/0-#4/0 | EA | 4 |  | 0
Point 13 | CNC-SNB-2 | Inst | CNC,Splice Non-Tension Bare,#6-#2 | EA | 2 |  | 0
Point 13 | CNC-NTS-2 | Inst | CNC, Non-Tension Splice for Serv,#6-#2 | EA | 4 |  | 0
Point 14 | PLA-CUT | Inst | PLA,Cut Off Pole Top | EA | 1 |  | 0
Point 15 | CNC-SNI-40 | Inst | CNC,Svc.spl. Non-Tension insul,#1/0-#4/0 | EA | 2 |  | 0
Point 15 | CNC-SNB-2 | Inst | CNC,Splice Non-Tension Bare,#6-#2 | EA | 2 |  | 0
Point 36 | PLA-CUT | Inst | PLA,Cut Off Pole Top | EA | 1 |  | 0
Point 35 | CNC-SNB-2 | Inst | CNC,Splice Non-Tension Bare,#6-#2 | EA | 6 |  | 0
Point36 | PLA-CUT | Inst | PLA,Cut Off Pole Top | EA | 1 |  | 0
Point 34 | PLA-CUT | Inst | PLA,Cut Off Pole Top | EA | 1 |  | 0
Point 32 | PLA-CUT | Inst | PLA,Cut Off Pole Top | EA | 1 |  | 0
point35 | CND-HC | Inst | #NO MATCH | #NO MATCH | 1 |  | 0
Point 36 | PLA-CUT | Inst | PLA,Cut Off Pole Top | EA | 0 |  | 0
Point 33 | CNC-SNB-2 | Inst | CNC,Splice Non-Tension Bare,#6-#2 | EA | 6 |  | 0
Point 33 | SVD-3-CV-C | Inst | SVD,3 inch,Clevis,Corr | EA | 1 |  | 0
Point 31 | CNC-SNB-2 | Inst | CNC,Splice Non-Tension Bare,#6-#2 | EA | 10 |  | 0
Point 31 | CNC-NTS-2 | Inst | CNC, Non-Tension Splice for Serv,#6-#2 | EA | 3 |  | 0
Point 30 | PLA-CUT | Inst | PLA,Cut Off Pole Top | EA | 0 |  | 0
Point 30 | PLA-CUT | Inst | PLA,Cut Off Pole Top | EA | 1 |  | 0
Point 01 | SVC-40-TP-ALA-PC | Trans | SVC,4/0,Trip,Alum/Aly Neut,Paral Comm | EA | 0 |  | 0
Point 05 | SVC-40-TP-ALA-PC | Trans | SVC,4/0,Trip,Alum/Aly Neut,Paral Comm | EA | 1 |  | 0
Point 07 | SVC-40-TP-ALA-PC | Trans | SVC,4/0,Trip,Alum/Aly Neut,Paral Comm | EA | 1 |  | 0
Point 09 | SVC-40-TP-ALA-PC | Trans | SVC,4/0,Trip,Alum/Aly Neut,Paral Comm | EA | 1 |  | 0
Point 11 | SVC-40-TP-ALA-PC | Trans | SVC,4/0,Trip,Alum/Aly Neut,Paral Comm | EA | 1 |  | 0
Point 13 | SVC-40-TP-ALA-PC | Trans | SVC,4/0,Trip,Alum/Aly Neut,Paral Comm | EA | 1 |  | 0
Point 29 | SVC-40-TP-ALA-PC | Trans | SVC,4/0,Trip,Alum/Aly Neut,Paral Comm | EA | 3 |  | 0
Point 03 | SVC-40-TP-ALA-PC | Trans | SVC,4/0,Trip,Alum/Aly Neut,Paral Comm | EA | 1 |  | 0
TOTAL | [6 empty] | 0