## Work Report
WEEKLY UNITS COMPLETED PER SCOPE ID
Report Generated On: 08/18/2025 09:49 PM
| REPORT SUMMARY |  |  |  | REPORT DETAILS
| Total Billed Amount: | 0 |  |  | Foreman: | Jose Rosenbaun Jr.
| Total Line Items: | 128 |  |  | Work Request #: | 89754704
| Billing Period: | 08/11/2025 to 08/17/25 |  |  | Scope ID #: | R25P80
[5 empty] | Work Order #: | DCP0371786
[5 empty] | Customer: | AEP
[5 empty] | Job #: | 570-2
Tuesday (08/12/2025)
Point Number | Billable Unit Code | Work Type | Unit Description | Unit of Measure | # Units | N/A | Pricing
Point 43 | PLA-HDIG | Inst | PLA,Hand Dig or Additional Excavation | EA | 1 |  | 0
Point 44 | PLA-CUT | Inst | PLA,Cut Off Pole Top | EA | 1 |  | 0
Point 43 | CNC-HTA-10 | Inst | Compression connector H-Tap Assembly 1/0 | EA | 8 |  | 0
Point 33 | ANC-DSC-24-120-D1 | Inst | ANC,Disc,24in,120in,Db Eye 1in | EA | 2 |  | 0
Point 43 | PLA-HDIG | Inst | PLA,Hand Dig or Additional Excavation | EA | 1 |  | 0
Point 43 | BKT-AC18-F | Inst | BKT,Arrestor/CO 18in (1Ph),Fbrgls | EA | 1 |  | 0
Point 43 | CND-HLC2 | Inst | CND,Hot Line clamp #6-#2 | EA | 1 |  | 0
Point 43 | CND-SA477 | Inst | CND,Stirrup,Ampact 477 | EA | 1 |  | 0
Point 43 | DEG-4-DP | Inst | DEG,#4,DuPlex | EA | 4 |  | 0
Point 43 | EQL-1-4-C-2-S-X | Inst | EQL,1 Ph,#4,CU Sol,#2,CU Str,Xfr | EA | 1 |  | 0
Point 43 | GND-CR-4 | Inst | GND,Cu Clad Rod,#4 | EA | 1 |  | 0
Point 43 | INS-15-P-S-C | Inst | INS,15kV,Pin,Silicon Polymer,Corr | EA | 3 |  | 0
Point 43 | PIN-15-PTP-K | Inst | Pin,15kV,Pole top,Contaminated | EA | 1 |  | 0
Point 43 | PIN-XAA | Inst | Pin,Crossarm,8in | EA | 2 |  | 0
Point 43 | PLD-EYE | Inst | PLD,Eyebolt Deadend | EA | 1 |  | 0
Point 43 | SVC-10-TP-AAA-RS | Tran | SVC,1/0,Trip,All Alum,Res | EA | 4 |  | 0
Point 44 | BKT-AC18-F | Rem | BKT,Arrestor/CO 18in (1Ph),Fbrgls | EA | 1 |  | 0
Point 44 | CND-HLC2 | Rem | CND,Hot Line clamp #6-#2 | EA | 1 |  | 0
Point 44 | CND-SA477 | Rem | CND,Stirrup,Ampact 477 | EA | 1 |  | 0
Point 44 | DEG-4-DP | Rem | DEG,#4,DuPlex | EA | 1 |  | 0
Point 44 | EQL-1-4-C-2-S-X | Rem | EQL,1 Ph,#4,CU Sol,#2,CU Str,Xfr | EA | 1 |  | 0
Point 44 | GND-CR-4 | Rem | GND,Cu Clad Rod,#4 | EA | 1 |  | 0
Point 44 | INS-15-P-S-C | Rem | INS,15kV,Pin,Silicon Polymer,Corr | EA | 3 |  | 0
Point 44 | PIN-15-PTP-K | Rem | Pin,15kV,Pole top,Contaminated | EA | 1 |  | 0
Point 44 | PIN-XAA | Rem | Pin,Crossarm,8in | EA | 2 |  | 0
Point 44 | POL-45-3 | Rem | Pole,45ft,Class 3 | EA | 0 |  | 0
Point 44 | SVC-VA | Rem | SVC-Virtual Asset Capitalization | EA | 2 |  | 0
Point 47 | CND-XL14 | Tran | CND,eXtension Link 14in | EA | 6 |  | 0
Point 47 | DEG-2-SNA | Inst | DEG,#2,Secondary Neutral Al | EA | 2 |  | 0
Point 47 | INS-15-P-S-C | Inst | INS,15kV,Pin,Silicon Polymer,Corr | EA | 3 |  | 0
Point 47 | PIN-15-PTP-K | Inst | Pin,15kV,Pole top,Contaminated | EA | 1 |  | 0
Point 47 | PIN-XAA | Inst | Pin,Crossarm,8in | EA | 2 |  | 0
Point 47 | POL-45-2 | Inst | Pole,45ft,Class 2 | EA | 1 |  | 0
Point 47 | SAA-3-CV | Inst | SAA,3 inch,Clevis | EA | 2 |  | 0
Point 47 | SWI-15-INL1-900-FW-556-H | Tran | 15kV,InLine,1Ph,900A,FireWdg, 477-556 Hk | EA | 9 |  | 0
Point 48 | PLA-CUT | Rem | PLA,Cut Off Pole Top | EA | 1 |  | 0
Point 48 | DEG-4-SNA | Rem | DEG,#4,Secondary Neutral Al | EA | 3 |  | 0
Point 48 | INS-15-P-S-C | Rem | INS,15kV,Pin,Silicon Polymer,Corr | EA | 3 |  | 0
Point 48 | PIN-15-PTP-K | Rem | Pin,15kV,Pole top,Contaminated | EA | 1 |  | 0
Point 48 | PIN-XAA | Rem | Pin,Crossarm,8in | EA | 2 |  | 0
Point 48 | PLD-EYE | Rem | PLD,Eyebolt Deadend | EA | 1 |  | 0
Point 48 | SAA-3-CV | Rem | SAA,3 inch,Clevis | EA | 1 |  | 0
Point 48 | SAA-DE-20 | Rem | SAA,DE Clamp #4-2/0 | EA | 1 |  | 0
Point 48 | TIE-4-ALH-F | Rem | TIE,4 AWG,AL Hand Tie,F Neck | EA | 24 |  | 0
Point 43 | ARM-8SF-GN-TL | Inst | ARM,8ft Sgl.Fiberglass,Gain,Tangent LD | EA | 1 |  | 0
Point 43 | POL-45-2 | Inst | Pole,45ft,Class 2 | EA | 1 |  | 0
Point 43 | SAA-3-CV | Inst | SAA,3 inch,Clevis | EA | 3 |  | 0
Point 43 | SVC-VA | Inst | SVC-Virtual Asset Capitalization | EA | 2 |  | 0
Point 43 | SVD-SG10 | Inst | SVD, Service Grip, 1/0 | EA | 2 |  | 0
Point 43 | TIE-4-ALH-F | Inst | TIE,4 AWG,AL Hand Tie,F Neck | EA | 24 |  | 0
Point 43 | XCO-15-100-7 | Inst | XCO,15kVPolymer,100 Amp,7kA | EA | 1 |  | 0
Point 44 | ARM-8S-60S | Rem | ARM,8ft Single Wood,60in Sgl.Wd | EA | 1 |  | 0
Point 44 | SAA-3-CV | Rem | SAA,3 inch,Clevis | EA | 2 |  | 0
Point 44 | SVD-SG10 | Rem | SVD, Service Grip, 1/0 | EA | 3 |  | 0
Point 44 | TIE-4-ALH-F | Rem | TIE,4 AWG,AL Hand Tie,F Neck | EA | 18 |  | 0
Point 44 | XCO-15-100-7 | Rem | XCO,15kVPolymer,100 Amp,7kA | EA | 1 |  | 0
Point 47 | ARM-8SF-GN-TL | Inst | ARM,8ft Sgl.Fiberglass,Gain,Tangent LD | EA | 1 |  | 0
Point 47 | CNW-FW-477-INL-SWI | Tran | Connector,Fired Wdg, 477 InLine SWI | EA | 6 |  | 0
Point 47 | DEG-4-SNA | Inst | DEG,#4,Secondary Neutral Al | EA | 3 |  | 0
Point 48 | ARM-8S-60S | Rem | ARM,8ft Single Wood,60in Sgl.Wd | EA | 1 |  | 0
Point 48 | PLA-HDIG | Inst | PLA,Hand Dig or Additional Excavation | EA | 1 |  | 0
Point 48 | POL-40-2 | Rem | Pole,40ft,Class 2 | EA | 0 |  | 0
TOTAL | [6 empty] | 0
Thursday (08/14/2025)
Point Number | Billable Unit Code | Work Type | Unit Description | Unit of Measure | # Units | N/A | Pricing
Point 35 | ANC-DSC-24-120-D1 | Inst | ANC,Disc,24in,120in,Db Eye 1in | EA | 2 |  | 0
Point 35 | PLA-HDIG | Inst | PLA,Hand Dig or Additional Excavation | EA | 2 |  | 0
Point 35 | CNC-HTA-10 | Inst | Compression connector H-Tap Assembly 1/0 | EA | 9 |  | 0
Point 33 | ANC-DSC-24-120-D1 | Inst | ANC,Disc,24in,120in,Db Eye 1in | EA | 2 |  | 0
Point 61 | PLA-HDIG | Inst | PLA,Hand Dig or Additional Excavation | EA | 1 |  | 0
Point 62 | PLA-CUT | Inst | PLA,Cut Off Pole Top | EA | 1 |  | 0
Point 35 | PLA-CUT | Inst | PLA,Cut Off Pole Top | EA | 1 |  | 0
Point 35 | ARM-8SF-GN-DL | Inst | ARM,8ft Sgl.Fiberglass,Gain,DE Light | EA | 1 |  | 0
Point 35 | ARR-10-R | Inst | ARR,10kV,Riser Pole | EA | 1 |  | 0
Point 35 | BKT-AC18-F | Inst | BKT,Arrestor/CO 18in (1Ph),Fbrgls | EA | 1 |  | 0
Point 35 | BKT-ARML-S | Inst | BKT,Crossarm inLin,Steel | EA | 1 |  | 0
Point 35 | CND-HLC2 | Inst | CND,Hot Line clamp #6-#2 | EA | 1 |  | 0
Point 35 | CND-SA477 | Inst | CND,Stirrup,Ampact 477 | EA | 1 |  | 0
Point 35 | DEC-795AL | Inst | DEC,#477 - #795 AL,AS | EA | 7 |  | 0
Point 35 | DEG-4-DP | Inst | DEG,#4,DuPlex | EA | 2 |  | 0
Point 35 | EQL-1-4-C-4-C-E1 | Inst | EQL,1 Phase,#4,Sol,#4,Sol,100a Eq C/O | EA | 1 |  | 0
Point 35 | GYD-MPY | Inst | GYD,Marker-Plastic-Yellow | EA | 2 |  | 0
Point 35 | GYF-38-D-78P-EP | Inst | GYF,3/8,Down,78in Pole mt,EyePlate | EA | 4 |  | 0
Point 35 | GYW-38 | Inst | GYW,3/8 in. EHS (15,400 lbs) | FT | 160 |  | 0
Point 35 | INS-15-P-S-C | Inst | INS,15kV,Pin,Silicon Polymer,Corr | EA | 3 |  | 0
Point 35 | PIN-XAA | Inst | Pin,Crossarm,8in | EA | 3 |  | 0
Point 35 | PLD-EYE | Inst | PLD,Eyebolt Deadend | EA | 1 |  | 0
Point 35 | SAA-DE-20 | Inst | SAA,DE Clamp #4-2/0 | EA | 2 |  | 0
Point 35 | SWI-15-CO1-100-H | Inst | SWI,15kV,Line Cutout 1PH,100A,Hook | EA | 1 |  | 0
Point 35 | TIE-4-ALH-F | Inst | TIE,4 AWG,AL Hand Tie,F Neck | EA | 18 |  | 0
Point 35 | URSR-2-DSO | Tran | URSR,2in,Dist Stand Off | EA | 2 |  | 0
Point 36 | ARM-8D-60S | Rem | ARM,8ft Double Wood,60in Sgl.Wd | EA | 1 |  | 0
Point 36 | ARR-10-R | Rem | ARR,10kV,Riser Pole | EA | 1 |  | 0
Point 36 | BKT-AC18-F | Rem | BKT,Arrestor/CO 18in (1Ph),Fbrgls | EA | 2 |  | 0
Point 36 | CND-HLC2 | Rem | CND,Hot Line clamp #6-#2 | EA | 4 |  | 0
Point 36 | CND-SA477 | Rem | CND,Stirrup,Ampact 477 | EA | 4 |  | 0
Point 36 | DEG-4-DP | Rem | DEG,#4,DuPlex | EA | 3 |  | 0
Point 36 | EQL-1-4-C-4-C-E1 | Rem | EQL,1 Phase,#4,Sol,#4,Sol,100a Eq C/O | EA | 1 |  | 0
Point 36 | GND-CR-4 | Rem | GND,Cu Clad Rod,#4 | EA | 1 |  | 0
Point 36 | GYD-MPY | Rem | GYD,Marker-Plastic-Yellow | EA | 2 |  | 0
Point 36 | GYF-38-D-78P-EP | Rem | GYF,3/8,Down,78in Pole mt,EyePlate | EA | 2 |  | 0
Point 36 | GYW-38 | Rem | GYW,3/8 in. EHS (15,400 lbs) | FT | 120 |  | 0
Point 36 | PLD-EYE | Rem | PLD,Eyebolt Deadend | EA | 1 |  | 0
Point 36 | SAA-DE-20 | Rem | SAA,DE Clamp #4-2/0 | EA | 2 |  | 0
Point 36 | SWI-15-CO1-100-H | Rem | SWI,15kV,Line Cutout 1PH,100A,Hook | EA | 1 |  | 0
Point 36 | UGND-TAG-C | Rem | UGND,TAG CABLE MARKER (WHITE),Cable | EA | 1 |  | 0
Point 61 | INS-15-P-S-C | Inst | INS,15kV,Pin,Silicon Polymer,Corr | EA | 3 |  | 0
Point 61 | PIN-15-PTP-K | Inst | Pin,15kV,Pole top,Contaminated | EA | 1 |  | 0
Point 61 | PIN-XAA | Inst | Pin,Crossarm,8in | EA | 2 |  | 0
Point 61 | POL-45-1 | Inst | Pole,45ft,Class 1 | EA | 1 |  | 0
Point 61 | SAA-3-CV | Inst | SAA,3 inch,Clevis | EA | 1 |  | 0
Point 61 | TIE-4-ALH-F | Inst | TIE,4 AWG,AL Hand Tie,F Neck | EA | 24 |  | 0
Point 62 | INS-15-P-S-C | Rem | INS,15kV,Pin,Silicon Polymer,Corr | EA | 3 |  | 0
Point 62 | PIN-15-PTP-K | Rem | Pin,15kV,Pole top,Contaminated | EA | 1 |  | 0
Point 62 | PIN-XAA | Rem | Pin,Crossarm,8in | EA | 2 |  | 0
Point 62 | POL-45-4 | Rem | Pole,45ft,Class 4 | EA | 0 |  | 0
Point 62 | SAA-3-CV | Rem | SAA,3 inch,Clevis | EA | 1 |  | 0
Point 62 | TIE-4-ALH-F | Rem | TIE,4 AWG,AL Hand Tie,F Neck | EA | 24 |  | 0
Point 35 | ALB-W-18-A-1-F | Tran | ALB,Wood mnt,18 in ,Alum,1Pos, Flood | EA | 1 |  | 0
Point 35 | ALT-1000-HFMSG | Tran | 1000W Halide Fldlt MultiVolt,Slipfit,Gry | EA | 1 |  | 0
Point 35 | ANC-DHM-8-84-D34 | Inst | ANC,Dbl Hlx Mach,8in,84in,Db Eye 3/4in | EA | 0 |  | 0
Point 35 | GND-CR-4 | Inst | GND,Cu Clad Rod,#4 | EA | 1 |  | 0
Point 36 | ANC-DHM-8-84-D34 | Rem | ANC,Dbl Hlx Mach,8in,84in,Db Eye 3/4in | EA | 2 |  | 0
Point 36 | GYF-38-D-N-GH | Rem | GYF,3/8,Down,None,Guy Hook | EA | 1 |  | 0
Point 36 | URSG-D-CP | Rem | URSG,Distr,Cable Postioner | EA | 1 |  | 0
Point 61 | ARM-8SF-GN-TL | Inst | ARM,8ft Sgl.Fiberglass,Gain,Tangent LD | EA | 1 |  | 0
Point 62 | ARM-8S-60S | Rem | ARM,8ft Single Wood,60in Sgl.Wd | EA | 1 |  | 0
TOTAL | [6 empty] | 0
Friday (08/15/2025)
Point Number | Billable Unit Code | Work Type | Unit Description | Unit of Measure | # Units | N/A | Pricing
Point 05 | ANC-DSC-24-120-D1 | Inst | ANC,Disc,24in,120in,Db Eye 1in | EA | 1 |  | 0
Point 05 | PLA-HDIG | Inst | PLA,Hand Dig or Additional Excavation | EA | 1 |  | 0
Point 41 | PLA-HDIG | Inst | PLA,Hand Dig or Additional Excavation | EA | 1 |  | 0
Point 05 | PLA-DLOC | Inst | PLA,Difficult Location | EA | 1 |  | 0
TOTAL | [6 empty] | 0