## Work Report
WEEKLY UNITS COMPLETED PER SCOPE ID
Report Generated On: 08/18/2025 09:48 PM
| REPORT SUMMARY |  |  |  | REPORT DETAILS
| Total Billed Amount: | 0 |  |  | Foreman: | Jose Rosenbaun Jr.
| Total Line Items: | 218 |  |  | Work Request #: | 89830464
| Billing Period: | 07/28/2025 to 08/03/25 |  |  | Scope ID #: | R25P146
[5 empty] | Work Order #: | DCP0371577
[5 empty] | Customer: | AEP
[5 empty] | Job #: | 570-1
Monday (07/28/2025)
Point Number | Billable Unit Code | Work Type | Unit Description | Unit of Measure | # Units | N/A | Pricing
Point 12 | CNC-HTA-10 | Inst | Compression connector H-Tap Assembly 1/0 | EA | 13 |  | 0
Point 09 | CNC-HTA-10 | Inst | Compression connector H-Tap Assembly 1/0 | EA | 19 |  | 0
Point 09 | CNC-SNB-40 | Inst | CNC,Splice Non-Tension Bare,#1/0-#4/0 | EA | 1 |  | 0
Point 09 | GND-CR-4 | Inst | GND,Cu Clad Rod,#4 | EA | 1 |  | 0
Point 09 | GND-MD | Inst | GND,Wire Mldg Only | EA | 2 |  | 0
Point 09 | INS-15-P-S-C | Inst | INS,15kV,Pin,Silicon Polymer,Corr | EA | 1 |  | 0
Point 09 | PIN-15-PTP-K | Inst | Pin,15kV,Pole top,Contaminated | EA | 1 |  | 0
Point 09 | PLD-EYE | Inst | PLD,Eyebolt Deadend | EA | 1 |  | 0
Point 09 | POL-40-2 | Inst | Pole,40ft,Class 2 | EA | 1 |  | 0
Point 09 | SAA-DE-20 | Inst | SAA,DE Clamp #4-2/0 | EA | 3 |  | 0
Point 09 | SVC-2-TP-ALA-RS | Tran | SVC,#2 AWG,Trip,Alum/Aly Neut,Res | EA | 6 |  | 0
Point 09 | SVC-VA | Inst | SVC-Virtual Asset Capitalization | EA | 5 |  | 0
Point 09 | SVD-3-CV-C | Inst | SVD,3 inch,Clevis,Corr | EA | 1 |  | 0
Point 09 | SVD-SG2 | Inst | SVD,Service Grip,#2 | EA | 8 |  | 0
Point 09 | PLA-CUT | Inst | PLA,Cut Off Pole Top | EA | 1 |  | 0
Point 10 | INS-15-P-S-C | Rem | INS,15kV,Pin,Silicon Polymer,Corr | EA | 1 |  | 0
Point 10 | PIN-15-PTP-K | Rem | Pin,15kV,Pole top,Contaminated | EA | 1 |  | 0
Point 10 | PLD-EYE | Rem | PLD,Eyebolt Deadend | EA | 1 |  | 0
Point 10 | POL-40-5 | Rem | Pole,40ft,Class 5 | EA | 0 |  | 0
Point 10 | SAA-3-CV | Rem | SAA,3 inch,Clevis | EA | 3 |  | 0
Point 10 | SAA-DE-20 | Rem | SAA,DE Clamp #4-2/0 | EA | 1 |  | 0
Point 10 | TIE-4-ALH-F | Rem | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 11 | ALB-W-18-A-1-F | Tran | ALB,Wood mnt,18 in ,Alum,1Pos, Flood | EA | 1 |  | 0
Point 11 | ALT-400-HFMSGL | Tran | 400W MultiVolt MH Fldlt,Slipfit,Grey,Pul | EA | 1 |  | 0
Point 11 | BKT-AC18-F | Inst | BKT,Arrestor/CO 18in (1Ph),Fbrgls | EA | 1 |  | 0
Point 11 | CND-HLC2 | Inst | CND,Hot Line clamp #6-#2 | EA | 1 |  | 0
Point 11 | CND-S2O | Inst | CND,Stirrup #2 Open | EA | 1 |  | 0
Point 11 | EQL-1-4-C-2-S-X | Inst | EQL,1 Ph,#4,CU Sol,#2,CU Str,Xfr | EA | 1 |  | 0
Point 11 | GND-CR-4 | Inst | GND,Cu Clad Rod,#4 | EA | 1 |  | 0
Point 11 | GND-MD | Inst | GND,Wire Mldg Only | EA | 2 |  | 0
Point 11 | INS-15-P-S-C | Inst | INS,15kV,Pin,Silicon Polymer,Corr | EA | 1 |  | 0
Point 11 | PIN-15-PTP-K | Inst | Pin,15kV,Pole top,Contaminated | EA | 1 |  | 0
Point 11 | POL-40-2 | Inst | Pole,40ft,Class 2 | EA | 1 |  | 0
Point 11 | SAA-3-CV | Inst | SAA,3 inch,Clevis | EA | 4 |  | 0
Point 11 | SVC-2-TP-ALA-RS | Tran | SVC,#2 AWG,Trip,Alum/Aly Neut,Res | EA | 4 |  | 0
Point 11 | SVC-VA | Inst | SVC-Virtual Asset Capitalization | EA | 3 |  | 0
Point 11 | SVD-3-CV-C | Inst | SVD,3 inch,Clevis,Corr | EA | 1 |  | 0
Point 11 | PLA-CUT | Inst | PLA,Cut Off Pole Top | EA | 1 |  | 0
Point 11 | DEG-2-SNA | Inst | DEG,#2,Secondary Neutral Al | EA | 6 |  | 0
Point 11 | XCO-15-100-7 | Inst | XCO,15kVPolymer,100 Amp,7kA | EA | 1 |  | 0
Point 11 | XFR-25-72-120-1B | Inst | XFR,25KVA,7.2/12.4kVY,120/240,1BG | EA | 1 |  | 0
Point 12 | BKT-AC18-F | Rem | BKT,Arrestor/CO 18in (1Ph),Fbrgls | EA | 1 |  | 0
Point 12 | CND-HLC2 | Rem | CND,Hot Line clamp #6-#2 | EA | 1 |  | 0
Point 12 | CND-S2O | Rem | CND,Stirrup #2 Open | EA | 1 |  | 0
Point 12 | DEC-20AL | Rem | DEC,#4 - #2/0 AA,AL,AS | EA | 2 |  | 0
Point 12 | EQL-1-4-C-2-S-X | Rem | EQL,1 Ph,#4,CU Sol,#2,CU Str,Xfr | EA | 1 |  | 0
Point 12 | INS-15-D-S-C | Rem | INS,15kV,Deadend,Polymer,Corr | EA | 2 |  | 0
Point 12 | INS-15-P-S-C | Rem | INS,15kV,Pin,Silicon Polymer,Corr | EA | 1 |  | 0
Point 12 | PIN-15-PTP-K | Rem | Pin,15kV,Pole top,Contaminated | EA | 1 |  | 0
Point 12 | PLD-EYE | Rem | PLD,Eyebolt Deadend | EA | 4 |  | 0
Point 12 | POL-40-5 | Rem | Pole,40ft,Class 5 | EA | 0 |  | 0
Point 12 | SAA-DE-20 | Rem | SAA,DE Clamp #4-2/0 | EA | 4 |  | 0
Point 12 | TIE-4-ALH-F | Rem | TIE,4 AWG,AL Hand Tie,F Neck | EA | 6 |  | 0
Point 12 | XCO-15-100-7 | Rem | XCO,15kVPolymer,100 Amp,7kA | EA | 1 |  | 0
Point 12 | XFR-25-72-120-1B | Rem | XFR,25KVA,7.2/12.4kVY,120/240,1BG | EA | 1 |  | 0
TOTAL | [6 empty] | 0
Tuesday (07/29/2025)
Point Number | Billable Unit Code | Work Type | Unit Description | Unit of Measure | # Units | N/A | Pricing
Point 03 | SAA-3-CV | Inst | SAA,3 inch,Clevis | EA | 1 |  | 0
Point 19 | SVC-2-TP-ALA-RS | Trans | SVC,#2 AWG,Trip,Alum/Aly Neut,Res | EA | 2 |  | 0
Point 19 | SVC-10-TP-AAA-RS | Trans | SVC,1/0,Trip,All Alum,Res | EA | 1 |  | 0
Point 19 | CNC-HTA-10 | Inst | Compression connector H-Tap Assembly 1/0 | EA | 17 |  | 0
Point 21 | SVC-2-TP-AAA-RS | Trans | SVC, #2 AWG ,Trip,Alum/Alloy Neut,RS | EA | 3 |  | 0
Point 21 | SVC-10-TP-AAA-RS | Trans | SVC,1/0,Trip,All Alum,Res | EA | 1 |  | 0
Point 21 | CNC-HTA-10 | Inst | Compression connector H-Tap Assembly 1/0 | EA | 18 |  | 0
Point 03 | CNC-HTA-10 | Inst | Compression connector H-Tap Assembly 1/0 | EA | 3 |  | 0
Point 03 | GND-MD | Inst | GND,Wire Mldg Only | EA | 2 |  | 0
Point 03 | INS-15-P-S-C | Inst | INS,15kV,Pin,Silicon Polymer,Corr | EA | 1 |  | 0
Point 03 | PLA-CUT | Inst | PLA,Cut Off Pole Top | EA | 1 |  | 0
Point 03 | PLA-HDIG | Inst | PLA,Hand Dig or Additional Excavation | EA | 1 |  | 0
Point 03 | POL-40-2 | Inst | Pole,40ft,Class 2 | EA | 1 |  | 0
Point 03 | PLA-HDIG | Inst | PLA,Hand Dig or Additional Excavation | EA | 1 |  | 0
Point 03 | TIE-4-ALH-F | Inst | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 04 | INS-15-P-S-C | Rem | INS,15kV,Pin,Silicon Polymer,Corr | EA | 1 |  | 0
Point 04 | PIN-15-PTP-K | Rem | Pin,15kV,Pole top,Contaminated | EA | 1 |  | 0
Point 04 | PLD-EYE | Rem | PLD,Eyebolt Deadend | EA | 2 |  | 0
Point 04 | POL-40-4 | Rem | Pole,40ft,Class 4 | EA | 0 |  | 0
Point 04 | SAA-CL-336 | Rem | SAA,Susp Clamp Light Angle,336 | EA | 1 |  | 0
Point 04 | SAA-DE-20 | Rem | SAA,DE Clamp #4-2/0 | EA | 1 |  | 0
Point 04 | TIE-4-ALH-F | Rem | TIE,4 AWG,AL Hand Tie,F Neck | EA | 12 |  | 0
Point 19 | DEG-2-SNA | Inst | DEG,#2,Secondary Neutral Al | EA | 3 |  | 0
Point 19 | ALT-LED-DD-T5-5L-SF | Tran | 5200L LED, Type 5, Dusk to Dawn | EA | 1 |  | 0
Point 19 | BKT-AC18-F | Inst | BKT,Arrestor/CO 18in (1Ph),Fbrgls | EA | 1 |  | 0
Point 19 | CND-HLC2 | Inst | CND,Hot Line clamp #6-#2 | EA | 1 |  | 0
Point 19 | CND-S2O | Inst | CND,Stirrup #2 Open | EA | 1 |  | 0
Point 19 | EQL-1-4-C-20-S-X | Inst | EQL,1 Ph,#4,CU Sol,2/0,CU Str,Xfr | EA | 1 |  | 0
Point 19 | GND-CR-4 | Inst | GND,Cu Clad Rod,#4 | EA | 1 |  | 0
Point 19 | GND-LG-AL | Inst | GND,Lug,Area Lt | EA | 1 |  | 0
Point 19 | GND-MD | Inst | GND,Wire Mldg Only | EA | 2 |  | 0
Point 19 | INS-15-P-S-C | Inst | INS,15kV,Pin,Silicon Polymer,Corr | EA | 1 |  | 0
Point 19 | PIN-15-PTP-K | Inst | Pin,15kV,Pole top,Contaminated | EA | 1 |  | 0
Point 19 | PLD-EYE | Inst | PLD,Eyebolt Deadend | EA | 1 |  | 0
Point 19 | POL-40-2 | Inst | Pole,40ft,Class 2 | EA | 1 |  | 0
Point 19 | PLA-CUT | Inst | PLA,Cut Off Pole Top | EA | 1 |  | 0
Point 19 | SAA-DE-20 | Inst | SAA,DE Clamp #4-2/0 | EA | 4 |  | 0
Point 19 | PLA-HDIG | Inst | PLA,Hand Dig or Additional Excavation | EA | 1 |  | 0
Point 19 | TIE-4-ALH-F | Inst | TIE,4 AWG,AL Hand Tie,F Neck | EA | 18 |  | 0
Point 19 | XCO-15-100-7 | Inst | XCO,15kVPolymer,100 Amp,7kA | EA | 1 |  | 0
Point 19 | XFR-50-72-120-1B | Tran | XFR,50KVA,7.2/12.4kVY,120/240,1BG | EA | 1 |  | 0
Point 20 | BKT-AC18-F | Rem | BKT,Arrestor/CO 18in (1Ph),Fbrgls | EA | 1 |  | 0
Point 20 | CND-HLC2 | Rem | CND,Hot Line clamp #6-#2 | EA | 1 |  | 0
Point 20 | CND-S2O | Rem | CND,Stirrup #2 Open | EA | 1 |  | 0
Point 20 | DEC-20AL | Rem | DEC,#4 - #2/0 AA,AL,AS | EA | 2 |  | 0
Point 20 | DEG-10-SNA | Rem | DEG,1/0,Secondary Neutral Al | EA | 4 |  | 0
Point 20 | EQL-1-4-C-2-S-X | Rem | EQL,1 Ph,#4,CU Sol,#2,CU Str,Xfr | EA | 1 |  | 0
Point 20 | INS-15-D-S-C | Rem | INS,15kV,Deadend,Polymer,Corr | EA | 2 |  | 0
Point 20 | INS-15-P-S-C | Rem | INS,15kV,Pin,Silicon Polymer,Corr | EA | 1 |  | 0
Point 20 | PIN-15-PTP-K | Rem | Pin,15kV,Pole top,Contaminated | EA | 1 |  | 0
Point 20 | PLD-EYE | Rem | PLD,Eyebolt Deadend | EA | 2 |  | 0
Point 20 | POL-40-5 | Rem | Pole,40ft,Class 5 | EA | 0 |  | 0
Point 20 | SAA-3-CV | Rem | SAA,3 inch,Clevis | EA | 4 |  | 0
Point 20 | TIE-4-ALH-F | Rem | TIE,4 AWG,AL Hand Tie,F Neck | EA | 18 |  | 0
Point 20 | XCO-15-100-7 | Rem | XCO,15kVPolymer,100 Amp,7kA | EA | 1 |  | 0
Point 21 | BKT-AC18-F | Tran | BKT,Arrestor/CO 18in (1Ph),Fbrgls | EA | 1 |  | 0
Point 21 | PLA-HDIG | Inst | PLA,Hand Dig or Additional Excavation | EA | 1 |  | 0
Point 21 | CND-S2O | Inst | CND,Stirrup #2 Open | EA | 1 |  | 0
Point 21 | DEG-2-SNA | Tran | DEG,#2,Secondary Neutral Al | EA | 1 |  | 0
Point 21 | GND-CR-4 | Inst | GND,Cu Clad Rod,#4 | EA | 1 |  | 0
Point 21 | PLA-CUT | Inst | PLA,Cut Off Pole Top | EA | 1 |  | 0
Point 21 | INS-15-P-S-C | Inst | INS,15kV,Pin,Silicon Polymer,Corr | EA | 1 |  | 0
Point 21 | PIN-15-PTP-K | Inst | Pin,15kV,Pole top,Contaminated | EA | 1 |  | 0
Point 21 | PLD-EYE | Inst | PLD,Eyebolt Deadend | EA | 1 |  | 0
Point 21 | POL-40-2 | Inst | Pole,40ft,Class 2 | EA | 1 |  | 0
Point 21 | SAA-3-CV | Inst | SAA,3 inch,Clevis | EA | 2 |  | 0
Point 21 | SAA-DE-20 | Inst | SAA,DE Clamp #4-2/0 | EA | 1 |  | 0
Point 21 | SVC-VA | Inst | SVC-Virtual Asset Capitalization | EA | 1 |  | 0
Point 21 | SVD-3-CV-C | Inst | SVD,3 inch,Clevis,Corr | EA | 1 |  | 0
Point 21 | SVD-SG2 | Inst | SVD,Service Grip,#2 | EA | 4 |  | 0
Point 21 | TIE-4-ALH-F | Inst | TIE,4 AWG,AL Hand Tie,F Neck | EA | 18 |  | 0
Point 21 | XCO-15-100-7 | Inst | XCO,15kVPolymer,100 Amp,7kA | EA | 1 |  | 0
Point 21 | XFR-25-72-120-1B | Tran | XFR,25KVA,7.2/12.4kVY,120/240,1BG | EA | 1 |  | 0
Point 22 | BKT-AC18-F | Rem | BKT,Arrestor/CO 18in (1Ph),Fbrgls | EA | 1 |  | 0
Point 22 | CND-HLC2 | Rem | CND,Hot Line clamp #6-#2 | EA | 1 |  | 0
Point 22 | CND-S2O | Rem | CND,Stirrup #2 Open | EA | 1 |  | 0
Point 22 | DEG-10-SNA | Rem | DEG,1/0,Secondary Neutral Al | EA | 4 |  | 0
Point 22 | EQL-1-4-C-2-S-X | Rem | EQL,1 Ph,#4,CU Sol,#2,CU Str,Xfr | EA | 1 |  | 0
Point 22 | INS-15-P-S-C | Rem | INS,15kV,Pin,Silicon Polymer,Corr | EA | 1 |  | 0
Point 22 | PIN-15-PTP-K | Rem | Pin,15kV,Pole top,Contaminated | EA | 1 |  | 0
Point 22 | POL-40-3 | Rem | Pole,40ft,Class 3 | EA | 0 |  | 0
Point 22 | SAA-3-CV | Rem | SAA,3 inch,Clevis | EA | 4 |  | 0
Point 22 | TIE-4-ALH-F | Rem | TIE,4 AWG,AL Hand Tie,F Neck | EA | 24 |  | 0
Point 22 | XCO-15-100-7 | Rem | XCO,15kVPolymer,100 Amp,7kA | EA | 1 |  | 0
TOTAL | [6 empty] | 0
Wednesday (07/30/2025)
Point Number | Billable Unit Code | Work Type | Unit Description | Unit of Measure | # Units | N/A | Pricing
Point 01 | SVC-2-TP-ALA-RS | Trans | SVC,#2 AWG,Trip,Alum/Aly Neut,Res | EA | 1 |  | 0
Point 01 | ALB-W-30-S-1-A | Tran | ALB,Wood,30in,Steel,1P,Area | EA | 1 |  | 0
Point 01 | ALT-150-SOP | Tran | ALT,100,Sodium,Open,120,SlipFit, pkg | EA | 1 |  | 0
Point 01 | ANC-DHM-10-84-D1 | Inst | ANC,Dbl Hlx Mach,10in,84in,Db Eye 1in | EA | 1 |  | 0
Point 01 | CNC-SNB-40 | Inst | CNC,Splice Non-Tension Bare,#1/0-#4/0 | EA | 2 |  | 0
Point 01 | DEC-20AL | Inst | DEC,#4 - #2/0 AA,AL,AS | EA | 1 |  | 0
Point 01 | DEG-10-SPA | Inst | DEG,1/0,Slack Span Alum | EA | 2 |  | 0
Point 01 | DEG-10-SPAJ | Inst | DEG, 1/0,Slack Span Alum for J-Neck Ins | EA | 1 |  | 0
Point 01 | GND-CR-4 | Inst | GND,Cu Clad Rod,#4 | EA | 1 |  | 0
Point 01 | GND-LG-AL | Inst | GND,Lug,Area Lt | EA | 1 |  | 0
Point 01 | GND-MD | Inst | GND,Wire Mldg Only | EA | 2 |  | 0
Point 01 | GYD-MPY | Inst | GYD,Marker-Plastic-Yellow | EA | 1 |  | 0
Point 01 | GYF-38-D-78P-EP | Inst | GYF,3/8,Down,78in Pole mt,EyePlate | EA | 2 |  | 0
Point 01 | CNC-HTA-10 | Inst | Compression connector H-Tap Assembly 1/0 | EA | 5 |  | 0
Point 01 | INS-15-D-S-C | Inst | INS,15kV,Deadend,Polymer,Corr | EA | 1 |  | 0
Point 01 | INS-15-P-S-C | Inst | INS,15kV,Pin,Silicon Polymer,Corr | EA | 1 |  | 0
Point 01 | PLA-CUT | Rem | PLA,Cut Off Pole Top | EA | 1 |  | 0
Point 01 | PLD-EYE |  | PLD,Eyebolt Deadend | EA | 3 |  | 0
Point 01 | POL-40-2 | Inst | Pole,40ft,Class 2 | EA | 1 |  | 0
Point 01 | SAA-3-CV | Inst | SAA,3 inch,Clevis | EA | 1 |  | 0
Point 01 | SAA-DE-20 | Inst | SAA,DE Clamp #4-2/0 | EA | 2 |  | 0
Point 02 | DEG-4-SPA | Rem | DEG,#4,Slack Span Alum | EA | 1 |  | 0
Point 02 | INS-15-P-S-C | Rem | INS,15kV,Pin,Silicon Polymer,Corr | EA | 1 |  | 0
Point 02 | PIN-15-PTP-K | Rem | Pin,15kV,Pole top,Contaminated | EA | 1 |  | 0
Point 02 | PLD-EYE | Rem | PLD,Eyebolt Deadend | EA | 3 |  | 0
Point 02 | POL-40-5 | Rem | Pole,40ft,Class 5 | EA | 0 |  | 0
Point 02 | SAA-3-CV | Rem | SAA,3 inch,Clevis | EA | 1 |  | 0
Point 02 | SAA-DE-20 | Rem | SAA,DE Clamp #4-2/0 | EA | 2 |  | 0
Point 02 | TIE-4-ALH-F | Rem | TIE,4 AWG,AL Hand Tie,F Neck | EA | 6 |  | 0
Point 05 | ALB-W-30-S-1-A | Tran | ALB,Wood,30in,Steel,1P,Area | EA | 1 |  | 0
Point 05 | ALT-LED-DD-T5-5L-SF | Tran | 5200L LED, Type 5, Dusk to Dawn | EA | 1 |  | 0
Point 05 | CNC-HTA-10 | Inst | Compression connector H-Tap Assembly 1/0 | EA | 13 |  | 0
Point 05 | BKT-AC18-F | Inst | BKT,Arrestor/CO 18in (1Ph),Fbrgls | EA | 1 |  | 0
Point 05 | CNC-SNB-40 | Inst | CNC,Splice Non-Tension Bare,#1/0-#4/0 | EA | 2 |  | 0
Point 05 | CND-HLC2 | Inst | CND,Hot Line clamp #6-#2 | EA | 1 |  | 0
Point 05 | CND-S2O | Inst | CND,Stirrup #2 Open | EA | 1 |  | 0
Point 05 | DEC-20AL | Inst | DEC,#4 - #2/0 AA,AL,AS | EA | 1 |  | 0
Point 05 | DEG-10-SPA | Inst | DEG,1/0,Slack Span Alum | EA | 1 |  | 0
Point 05 | DEG-10-SPAJ | Inst | DEG, 1/0,Slack Span Alum for J-Neck Ins | EA | 4 |  | 0
Point 05 | EQL-1-4-C-2-S-X | Inst | EQL,1 Ph,#4,CU Sol,#2,CU Str,Xfr | EA | 1 |  | 0
Point 05 | GND-CR-4 | Inst | GND,Cu Clad Rod,#4 | EA | 1 |  | 0
Point 05 | GND-LG-AL | Inst | GND,Lug,Area Lt | EA | 1 |  | 0
Point 05 | GND-MD | Inst | GND,Wire Mldg Only | EA | 2 |  | 0
Point 05 | GYD-MPY | Inst | GYD,Marker-Plastic-Yellow | EA | 1 |  | 0
Point 05 | GYF-38-D-78P-EP | Inst | GYF,3/8,Down,78in Pole mt,EyePlate | EA | 1 |  | 0
Point 05 | GYW-38 | Inst | GYW,3/8 in. EHS (15,400 lbs) | FT | 40 |  | 0
Point 05 | INS-15-D-S-C | Inst | INS,15kV,Deadend,Polymer,Corr | EA | 1 |  | 0
Point 05 | INS-15-P-S-C | Inst | INS,15kV,Pin,Silicon Polymer,Corr | EA | 1 |  | 0
Point 05 | PIN-15-PTP-K | Inst | Pin,15kV,Pole top,Contaminated | EA | 1 |  | 0
Point 05 | PLD-EYE | Inst | PLD,Eyebolt Deadend | EA | 3 |  | 0
Point 05 | POL-40-2 | Inst | Pole,40ft,Class 2 | EA | 1 |  | 0
Point 05 | SAA-3-CV | Inst | SAA,3 inch,Clevis | EA | 1 |  | 0
Point 05 | SAA-DE-20 | Inst | SAA,DE Clamp #4-2/0 | EA | 2 |  | 0
Point 05 | SVC-2-TP-ALA-RS | Tran | SVC,#2 AWG,Trip,Alum/Aly Neut,Res | EA | 2 |  | 0
Point 05 | SVC-VA | Inst | SVC-Virtual Asset Capitalization | EA | 2 |  | 0
Point 05 | PLA-CUT | Inst | PLA,Cut Off Pole Top | EA | 1 |  | 0
Point 05 | PLA-HDIG | Inst | PLA,Hand Dig or Additional Excavation | EA | 2 |  | 0
Point 05 | XCO-15-100-7 | Inst | XCO,15kVPolymer,100 Amp,7kA | EA | 1 |  | 0
Point 05 | XFR-25-72-120-1B | Tran | XFR,25KVA,7.2/12.4kVY,120/240,1BG | EA | 1 |  | 0
Point 06 | ANC-DHM-10-84-D1 | Rem | ANC,Dbl Hlx Mach,10in,84in,Db Eye 1in | EA | 1 |  | 0
Point 06 | BKT-AC18-F | Rem | BKT,Arrestor/CO 18in (1Ph),Fbrgls | EA | 1 |  | 0
Point 06 | CND-HLC2 | Rem | CND,Hot Line clamp #6-#2 | EA | 1 |  | 0
Point 06 | CND-S2O | Rem | CND,Stirrup #2 Open | EA | 1 |  | 0
Point 06 | CON-2-AAA-1-B-REEL | Rem | CON,#2 AWG,Alum Alloy,One,Bare,Reels | FT | 72 |  | 0
Point 06 | DEC-20AL | Rem | DEC,#4 - #2/0 AA,AL,AS | EA | 1 |  | 0
Point 06 | DEG-2-SPAJ | Rem | DEG,#2,Slack span Alum for J-neck | EA | 1 |  | 0
Point 06 | DEG-4-SPA | Rem | DEG,#4,Slack Span Alum | EA | 1 |  | 0
Point 06 | EQL-1-4-C-2-S-X | Rem | EQL,1 Ph,#4,CU Sol,#2,CU Str,Xfr | EA | 1 |  | 0
Point 06 | GYD-MPY | Rem | GYD,Marker-Plastic-Yellow | EA | 1 |  | 0
Point 06 | GYF-38-D-78P-EP | Rem | GYF,3/8,Down,78in Pole mt,EyePlate | EA | 1 |  | 0
Point 06 | GYW-38 | Rem | GYW,3/8 in. EHS (15,400 lbs) | FT | 40 |  | 0
Point 06 | INS-15-D-S-C | Rem | INS,15kV,Deadend,Polymer,Corr | EA | 1 |  | 0
Point 06 | INS-15-P-S-C | Rem | INS,15kV,Pin,Silicon Polymer,Corr | EA | 1 |  | 0
Point 06 | PIN-15-PTP-K | Rem | Pin,15kV,Pole top,Contaminated | EA | 1 |  | 0
Point 06 | PLD-EYE | Rem | PLD,Eyebolt Deadend | EA | 2 |  | 0
Point 06 | POL-40-5 | Rem | Pole,40ft,Class 5 | EA | 0 |  | 0
Point 06 | SAA-3-CV | Rem | SAA,3 inch,Clevis | EA | 1 |  | 0
Point 06 | SAA-DE-20 | Rem | SAA,DE Clamp #4-2/0 | EA | 1 |  | 0
Point 06 | XCO-15-100-7 | Rem | XCO,15kVPolymer,100 Amp,7kA | EA | 1 |  | 0
TOTAL | [6 empty] | 0