## Work Report
WEEKLY UNITS COMPLETED PER SCOPE ID
Report Generated On: 07/30/2025 01:48 PM
| REPORT SUMMARY |  |  |  | REPORT DETAILS
| Total Billed Amount: | 15086.45 |  |  | Foreman: | Karl Guidroz
| Total Line Items: | 96 |  |  | Work Request #: | 89732091
| Billing Period: | 07/27/2025 to 07/27/25 |  |  | Scope ID #: | R25P11
[5 empty] | Work Order #: | DCP0371513
[5 empty] | Customer: | AEP
[5 empty] | Job #: | 704-1
Thursday (07/24/2025)
Point Number | Billable Unit Code | Work Type | Unit Description | Unit of Measure | # Units | N/A | Pricing
Point 05 | ARM-8SF-GN-DL-C | Inst | ARM,8ftSgl.Fiberglass,Gain,DE Light,Corr | EA | 1 |  | 350.53
Point 05 | BKT-AC18-F-C | Inst | BKT,Arrestor/CO 18in (1Ph),Fbrgls,Corr | EA | 2 |  | 63.44
Point 05 | GYF-38-D-42P-EP-C | Inst | GYF,3/8,Down,42in Pole mt,EyePlate,Corr | EA | 1 |  | 79.35
Point 11 | BKT-AC18-F-C | Inst | BKT,Arrestor/CO 18in (1Ph),Fbrgls,Corr | EA | 1 |  | 31.72
Point 15 | DEC-20AL-C | Inst | DEC,#4 - #2/0 AA,AL,AS,Corrosive | EA | 1 |  | 286.25
Point 15 | GYF-38-D-42P-EP-C | Inst | GYF,3/8,Down,42in Pole mt,EyePlate,Corr | EA | 1 |  | 79.35
Point 15 | SVD-SG2 | Inst | SVD,Service Grip,#2 | EA | 3 |  | 858.75
Point 15 | BKT-AC18-F-C | Inst | BKT,Arrestor/CO 18in (1Ph),Fbrgls,Corr | EA | 1 |  | 31.72
TOTAL | [6 empty] | 1781.11
Friday (07/25/2025)
Point Number | Billable Unit Code | Work Type | Unit Description | Unit of Measure | # Units | N/A | Pricing
Point 05 | CON-10-AAA-1-B-REEL | Inst | CON,#1/0 AWG,Alum Alloy,One,Bare,Reel | FT | 142 |  | 332.28
Point 05 | DEC-20AL-C | Inst | DEC,#4 - #2/0 AA,AL,AS,Corrosive | EA | 3 |  | 858.75
Point 07 | CON-10-AAA-1-B-REEL | Inst | CON,#1/0 AWG,Alum Alloy,One,Bare,Reel | FT | 49 |  | 114.66
Point 07 | CON-10-AAA-3-P | Inst | CON,#1/0 AWG,Alum Alloy,Three,Poly | FT | 49 |  | 35.28
Point 07 | SAA-DE-20-C | Inst | SAA,DE Clamp #4-2/0, Corr. | EA | 2 |  | 110.36
Point 11 | CND-SA10 | Inst | CND,Stirrup,Ampact,1/0 | EA | 1 |  | 12.49
Point 11 | CON-10-AAA-1-B-REEL | Inst | CON,#1/0 AWG,Alum Alloy,One,Bare,Reel | FT | 95 |  | 222.3
Point 11 | CON-10-AAA-3-P | Inst | CON,#1/0 AWG,Alum Alloy,Three,Poly | FT | 95 |  | 68.4
Point 11 | EQL-1-4-C-2-S-X-C | Inst | EQL,1 Ph,#4,CU Sol,#2,CU Str,Xfr,Corr | EA | 1 |  | 223
Point 11 | SVD-SG2 | Inst | SVD,Service Grip,#2 | EA | 1 |  | 286.25
Point 13 | CON-10-AAA-1-B-REEL | Inst | CON,#1/0 AWG,Alum Alloy,One,Bare,Reel | FT | 125 |  | 292.5
Point 13 | GYF-38-D-42P-EP-C | Inst | GYF,3/8,Down,42in Pole mt,EyePlate,Corr | EA | 1 |  | 79.35
Point 13 | SAA-3-CV-C | Inst | SAA,3 inch,Clevis,Corr | EA | 1 |  | 55.18
Point 15 | SAA-DE-20-C | Inst | SAA,DE Clamp #4-2/0, Corr. | EA | 4 |  | 220.72
Point 15 | XFR-25-72-120-1B-S | Inst | XFR,25KVA,7.2/12.4kVY,120/240,1BG,SS | EA | 1 |  | 234
TOTAL | [6 empty] | 3145.52
Saturday (07/26/2025)
Point Number | Billable Unit Code | Work Type | Unit Description | Unit of Measure | # Units | N/A | Pricing
Point 05 | INS-15-P-S-C | Inst | INS,15kV,Pin,Silicon Polymer,Corr | EA | 1 |  | 94.17
Point 05 | PIN-XAL-C | Inst | Pin,Crossarm Light,Corrosive | EA | 1 |  | 94.17
Point 05 | SAA-DI-10-C | Inst | SAA,Dead End I Bolt,1/0,Corr | EA | 2 |  | 110.36
Point 05 | SVD-SG2 | Inst | SVD,Service Grip,#2 | EA | 1 |  | 286.25
Point 08 | CON-2-AAA-1-B-REEL | Rem | CON,#2 AWG,Alum Alloy,One,Bare,Reels | FT | 54 |  | 50.22
Point 08 | INS-15-P-S-C | Rem | INS,15kV,Pin,Silicon Polymer,Corr | EA | 1 |  | 31.08
Point 08 | PIN-15-PTP-C | Rem | Pin,15kV,Pole top,Corrosive | EA | 1 |  | 31.08
Point 09 | CON-10-AAA-1-B-REEL | Inst | CON,#1/0 AWG,Alum Alloy,One,Bare,Reel | FT | 38 |  | 88.92
Point 09 | CON-10-AAA-3-P | Inst | CON,#1/0 AWG,Alum Alloy,Three,Poly | FT | 38 |  | 27.36
Point 09 | SAA-3-CV-C | Inst | SAA,3 inch,Clevis,Corr | EA | 1 |  | 55.18
Point 10 | CON-2-AAA-1-B | Rem | CON,#2 AWG,Alum Alloy,One,Bare,Coils | FT | 38 |  | 35.34
Point 10 | CON-2-AAA-1-B-REEL | Rem | CON,#2 AWG,Alum Alloy,One,Bare,Reels | FT | 38 |  | 35.34
Point 10 | CON-4-CHD-1-B | Rem | CON,#4,CU Hard Dr,One,Bare(Rem+Spl only) | FT | 114 |  | 106.02
Point 10 | INS-15-P-S-C | Rem | INS,15kV,Pin,Silicon Polymer,Corr | EA | 1 |  | 31.08
Point 10 | PIN-15-PTP-C | Rem | Pin,15kV,Pole top,Corrosive | EA | 1 |  | 31.08
Point 10 | SAA-3-CV-C | Rem | SAA,3 inch,Clevis,Corr | EA | 1 |  | 17.2
Point 11 | SAA-3-CV-C | Inst | SAA,3 inch,Clevis,Corr | EA | 1 |  | 55.18
Point 11 | SAA-DE-20-C | Inst | SAA,DE Clamp #4-2/0, Corr. | EA | 1 |  | 55.18
Point 12 | BKT-AC18-F-C | Rem | BKT,Arrestor/CO 18in (1Ph),Fbrgls,Corr | EA | 1 |  | 17.37
Point 12 | CON-2-AAA-1-B-REEL | Rem | CON,#2 AWG,Alum Alloy,One,Bare,Reels | FT | 102 |  | 94.86
Point 12 | CON-4-CHD-1-B | Rem | CON,#4,CU Hard Dr,One,Bare(Rem+Spl only) | FT | 306 |  | 284.58
Point 12 | INS-15-P-S-C | Rem | INS,15kV,Pin,Silicon Polymer,Corr | EA | 1 |  | 31.08
Point 12 | PIN-15-PTP-C | Rem | Pin,15kV,Pole top,Corrosive | EA | 1 |  | 31.08
Point 12 | SAA-3-CV-C | Rem | SAA,3 inch,Clevis,Corr | EA | 1 |  | 17.2
Point 13 | CON-10-AAA-3-P | Inst | CON,#1/0 AWG,Alum Alloy,Three,Poly | FT | 125 |  | 90
Point 13 | CON-2-AAA-2-P | Inst | CON,#2 AWG,Alum Alloy,Two,Poly | FT | 173 |  | 124.56
Point 13 | SAA-DE-20-C | Inst | SAA,DE Clamp #4-2/0, Corr. | EA | 1 |  | 55.18
Point 14 | CON-2-AAA-1-B | Rem | CON,#2 AWG,Alum Alloy,One,Bare,Coils | FT | 118 |  | 109.74
Point 15 | SVC-2-TP-ALA-RS | Tran | SVC,#2 AWG,Trip,Alum/Aly Neut,Res | EA | 3 |  | 587.49
Point 15 | SVD-3-CV-C | Tran | SVD,3 inch,Clevis,Corr | EA | 3 |  | 140.16
Point 16 | DEC-20CU | Rem | DEC,#6 - #2/0 CU | EA | 1 |  | 95.15
Point 17 | SAA-DE-20-C | Inst | SAA,DE Clamp #4-2/0, Corr. | EA | 1 |  | 55.18
TOTAL | [6 empty] | 2968.84
Sunday (07/27/2025)
Point Number | Billable Unit Code | Work Type | Unit Description | Unit of Measure | # Units | N/A | Pricing
Point 06 | DEC-20AL-C | Rem | DEC,#4 - #2/0 AA,AL,AS,Corrosive | EA | 3 |  | 285.45
Point 07 | CNC-SNB-10 | Inst | CNC,Splice Non-Tension Bare,#336-#1033 | EA | 1 |  | 20.29
Point 07 | SVC-2-TP-ALA-RS | Tran | SVC,#2 AWG,Trip,Alum/Aly Neut,Res | EA | 1 |  | 195.83
Point 07 | SVD-3-CV-C | Tran | SVD,3 inch,Clevis,Corr | EA | 1 |  | 46.72
Point 08 | CON-2-AAA-1-B | Rem | CON,#2 AWG,Alum Alloy,One,Bare,Coils | FT | 54 |  | 50.22
Point 08 | CON-4-CHD-1-B | Rem | CON,#4,CU Hard Dr,One,Bare(Rem+Spl only) | FT | 162 |  | 150.66
Point 08 | POL-35-5 | Rem | Pole,35ft,Class 5 | EA | 1 |  | 198.88
Point 08 | SAA-DE-20-C | Rem | SAA,DE Clamp #4-2/0, Corr. | EA | 2 |  | 34.4
Point 09 | SVC-2-TP-ALA-RS | Tran | SVC,#2 AWG,Trip,Alum/Aly Neut,Res | EA | 1 |  | 195.83
Point 09 | SVD-3-CV-C | Tran | SVD,3 inch,Clevis,Corr | EA | 1 |  | 46.72
Point 10 | POL-35-5 | Rem | Pole,35ft,Class 5 | EA | 1 |  | 198.88
Point 11 | SVC-2-TP-ALA-RS | Tran | SVC,#2 AWG,Trip,Alum/Aly Neut,Res | EA | 1 |  | 195.83
Point 11 | SVD-3-CV-C | Tran | SVD,3 inch,Clevis,Corr | EA | 1 |  | 46.72
Point 11 | XCO-15-100-7 | Inst | XCO,15kVPolymer,100 Amp,7kA | EA | 1 |  | 62.42
Point 11 | XFR-25-72-120-1B | Inst | XFR,25KVA,7.2/12.4kVY,120/240,1BG | EA | 1 |  | 234
Point 12 | CND-S2O | Rem | CND,Stirrup #2 Open | EA | 1 |  | 6.17
Point 12 | CON-2-AAA-1-B | Rem | CON,#2 AWG,Alum Alloy,One,Bare,Coils | FT | 102 |  | 94.86
Point 12 | EQL-1-4-C-2-S-X-C | Rem | EQL,1 Ph,#4,CU Sol,#2,CU Str,Xfr,Corr | EA | 1 |  | 116
Point 12 | GND-CR-4 | Rem | GND,Cu Clad Rod,#4 | EA | 1 |  | 60.43
Point 12 | POL-40-5 | Rem | Pole,40ft,Class 5 | EA | 1 |  | 198.88
Point 12 | XCO-15-100-7 | Rem | XCO,15kVPolymer,100 Amp,7kA | EA | 1 |  | 26.52
Point 12 | XFR-25-72-120-1B | Rem | XFR,25KVA,7.2/12.4kVY,120/240,1BG | EA | 1 |  | 159
Point 13 | SVD-3-CV-C | Tran | SVD,3 inch,Clevis,Corr | EA | 1 |  | 46.72
Point 14 | CON-2-AAA-1-B-REEL | Rem | CON,#2 AWG,Alum Alloy,One,Bare,Reels | FT | 118 |  | 109.74
Point 14 | CON-4-AAA-1-W | Rem | CON,#4 AWG,Alum Alloy,One,WP | FT | 348 |  | 323.64
Point 14 | CON-4-CHD-1-B | Rem | CON,#4,CU Hard Dr,One,Bare(Rem+Spl only) | FT | 354 |  | 329.22
Point 14 | INS-15-P-S-C | Rem | INS,15kV,Pin,Silicon Polymer,Corr | EA | 1 |  | 31.08
Point 14 | PIN-15-PTP-C | Rem | Pin,15kV,Pole top,Corrosive | EA | 1 |  | 31.08
Point 14 | SAA-3-CV-C | Rem | SAA,3 inch,Clevis,Corr | EA | 1 |  | 17.2
Point 16 | POL-40-4 | Rem | Pole,40ft,Class 4 | EA | 1 |  | 198.88
Point 17 | SAA-DE-20-C | Rem | SAA,DE Clamp #4-2/0, Corr. | EA | 2 |  | 34.4
Point 05 | CND-PBC10A | Inst | CND,Pri.Breaker Clamp #4-1/0 AL | EA | 1 |  | 286.25
Point 07 | CND-PBC10A | Inst | CND,Pri.Breaker Clamp #4-1/0 AL | EA | 2 |  | 572.5
Point 13 | CND-PBC10A | Inst | CND,Pri.Breaker Clamp #4-1/0 AL | EA | 2 |  | 572.5
Point 15 | CND-PBC10A | Inst | CND,Pri.Breaker Clamp #4-1/0 AL | EA | 2 |  | 572.5
Point 17 | CND-PBC10A-C | Inst | CND,Pri.BreakerClamp #4-1/0 AL,Corrosive | EA | 3 |  | 858.75
Point 15 | CND-PBC10A-C | Inst | CND,Pri.BreakerClamp #4-1/0 AL,Corrosive | EA | 1 |  | 286.25
Point 09 | CND-SNI-40 | Inst | #NO MATCH | #NO MATCH | 1 |  | 27.6
Point 09 | CNC-HTA-40 | Inst | Compression Connector H-Tap Assembly 4/0 | EA | 4 |  | 38.28
Point 11 | CNC-HTA-40 | Inst | Compression Connector H-Tap Assembly 4/0 | EA | 12 |  | 114.84
Point 15 | CNC-HTA-40 | Inst | Compression Connector H-Tap Assembly 4/0 | EA | 12 |  | 114.84
TOTAL | [6 empty] | 7190.98