## Work Report
WEEKLY UNITS COMPLETED PER SCOPE ID
Report Generated On: 08/16/2025 12:48 AM
| REPORT SUMMARY |  |  |  | REPORT DETAILS
| Total Billed Amount: | 15293.24 |  |  | Foreman: | Devin Carriere
| Total Line Items: | 51 |  |  | Work Request #: | 89713058
| Billing Period: | 08/11/2025 to 08/17/25 |  |  | Scope ID #: | R25P16
[5 empty] | Work Order #: | DCP0371565
[5 empty] | Customer: | AEP
[5 empty] | Job #: | 820-1
Tuesday (08/12/2025)
Point Number | Billable Unit Code | Work Type | Unit Description | Unit of Measure | # Units | N/A | Pricing
Point 01 | CNC-SNB-2 | Inst | CNC,Splice Non-Tension Bare,#6-#2 | EA | 4 |  | 81.16
Point 01 | CNC-SNB-40 | Inst | CNC,Splice Non-Tension Bare,#1/0-#4/0 | EA | 1 |  | 20.29
Point 01 | CND-S2O | Inst | CND,Stirrup #2 Open | EA | 3 |  | 82.8
Point 01 | DEC-20AL-C | Inst | DEC,#4 - #2/0 AA,AL,AS,Corrosive | EA | 3 |  | 858.75
Point 01 | SWI-27-CO1-100-H-C | Inst | SWI,27kV,Line Cutout 1PH,100A,Hook,C | EA | 3 |  | 187.26
Point 11 | BKT-AC24-F-C | Inst | BKT,Arrestor/CO 24in (1Ph),Fbrgls,Corr | EA | 1 |  | 31.72
Point 11 | CND-S2O | Inst | CND,Stirrup #2 Open | EA | 1 |  | 27.6
Point 11 | EQL-1-4-C-2-S-X-C | Inst | EQL,1 Ph,#4,CU Sol,#2,CU Str,Xfr,Corr | EA | 1 |  | 223
Point 11 | SAA-3-CV-C | Inst | SAA,3 inch,Clevis,Corr | EA | 1 |  | 55.18
Point 11 | SVC-10-TP-AAA-RS | Tran | SVC,1/0,Trip,All Alum,Res | EA | 3 |  | 587.49
Point 11 | SVD-3-CV | Inst | SVD,3 inch,Clevis | EA | 2 |  | 110.36
Point 11 | USVC-TRS | Tran | USVC,Terminate Service at Source | EA | 1 |  | 16.52
Point 11 | XCO-27-100-8-C | Inst | XCO,27kV Polymer,100 Amp,8kA, Corrosive | EA | 1 |  | 62.42
Point 11 | XFR-25-72-120-1B-S | Inst | XFR,25KVA,7.2/12.4kVY,120/240,1BG,SS | EA | 1 |  | 234
Point 12 | BKT-AC18-F | Rem | BKT,Arrestor/CO 18in (1Ph),Fbrgls | EA | 1 |  | 17.37
Point 12 | CND-S2O | Rem | CND,Stirrup #2 Open | EA | 1 |  | 6.17
Point 12 | EQL-1-4-C-2-S-X-C | Rem | EQL,1 Ph,#4,CU Sol,#2,CU Str,Xfr,Corr | EA | 1 |  | 116
Point 12 | GND-CR-4 | Rem | GND,Cu Clad Rod,#4 | EA | 1 |  | 60.43
Point 12 | INS-15-P-S-C | Rem | INS,15kV,Pin,Silicon Polymer,Corr | EA | 1 |  | 31.08
Point 12 | PIN-15-PTP-C | Rem | Pin,15kV,Pole top,Corrosive | EA | 1 |  | 31.08
Point 12 | SAA-3-CV-C | Rem | SAA,3 inch,Clevis,Corr | EA | 2 |  | 34.4
Point 12 | SVD-SG10 | Rem | SVD, Service Grip, 1/0 | EA | 3 |  | 285.45
Point 12 | XCO-27-100-8-C | Rem | XCO,27kV Polymer,100 Amp,8kA, Corrosive | EA | 1 |  | 26.52
Point 11 | XFR-25-72-120-1B-S | Rem | XFR,25KVA,7.2/12.4kVY,120/240,1BG,SS | EA | 1 |  | 159
Point 11 | PLA-DLOC | Inst | PLA,Difficult Location | EA | 1 |  | 119.1
Point 12 | PLA-DLOC | Inst | PLA,Difficult Location | EA | 2 |  | 238.2
12 | PLA-CUT | Inst | PLA,Cut Off Pole Top | EA | 1 |  | 216.17
Point 12 | PLA-BACK | Inst | Difficult Location Equip Adder-Backyard | EA | 20 |  | 2382
TOTAL | [6 empty] | 6301.52
Wednesday (08/13/2025)
Point Number | Billable Unit Code | Work Type | Unit Description | Unit of Measure | # Units | N/A | Pricing
Point 03 | SVD-SG40 | Inst | SVD, Service Grip, 4/0 | EA | 3 |  | 858.75
Point 03 | SVD-SG40 | Rem | SVD, Service Grip, 4/0 | EA | 3 |  | 285.45
Point 03 | SVC-40-QD-ALA-CM | Trans | SVC,4/0,Quad,Alum/Aly Neut,Comm | EA | 3 |  | 587.49
Point 11 | SVD-SG2 | Inst | SVD,Service Grip,#2 | EA | 3 |  | 858.75
Point 11 | SVD-SG2 | Rem | SVD,Service Grip,#2 | EA | 3 |  | 285.45
Point 11 | CNC-HTA3-10 | Inst | Compression Conn H-Tap Assembly 3ph 1/0 | EA | 15 |  | 143.55
Point 11 | SVC-2-TP-AAL-RS | Trans | SVC,#2 AWG,Trip,All Alum,Res | EA | 3 |  | 587.49
Point 13 | SVD-SG2 | Inst | SVD,Service Grip,#2 | EA | 3 |  | 858.75
Point 13 | SVD-SG2 | Rem | SVD,Service Grip,#2 | EA | 3 |  | 285.45
Point 13 | CNC-HTA3-10 | Inst | Compression Conn H-Tap Assembly 3ph 1/0 | EA | 6 |  | 57.42
Point 13 | CNC-HTA3-10 | Rem | Compression Conn H-Tap Assembly 3ph 1/0 | EA | 6 |  | 36.6
Point 13 | SVC-2-TP-AAL-RS | Trans | SVC,#2 AWG,Trip,All Alum,Res | EA | 3 |  | 587.49
Point 17 | SVC-40-QD-ALA-CM | Trans | SVC,4/0,Quad,Alum/Aly Neut,Comm | EA | 1 |  | 195.83
Point 17 | SVD-SG40 | Inst | SVD, Service Grip, 4/0 | EA | 1 |  | 286.25
Point 17 | SVD-SG40 | Rem | SVD, Service Grip, 4/0 | EA | 1 |  | 95.15
Point 21 | SVC-10-TP-AAL-RS | Trans | SVC,1/0,Trip,All Alum,Res | EA | 2 |  | 391.66
Point 21 | SVD-SG10 | Rem | SVD, Service Grip, 1/0 | EA | 2 |  | 190.3
Point 21 | DEC-20AL | Inst | DEC,#4 - #2/0 AA,AL,AS | EA | 2 |  | 572.5
Point 21 | CNC-HTA3-10 | Inst | Compression Conn H-Tap Assembly 3ph 1/0 | EA | 4 |  | 38.28
Point 27 | SVC-40-QD-ALA-CM | Trans | SVC,4/0,Quad,Alum/Aly Neut,Comm | EA | 3 |  | 587.49
Point 27 | SVD-SG40 | Inst | SVD, Service Grip, 4/0 | EA | 3 |  | 858.75
Point 27 | SVD-SG40 | Rem | SVD, Service Grip, 4/0 | EA | 3 |  | 285.45
Point 27 | CNC-HTA3-10 | Inst | Compression Conn H-Tap Assembly 3ph 1/0 | EA | 6 |  | 57.42
TOTAL | [6 empty] | 8991.72