## Work Report
WEEKLY UNITS COMPLETED PER SCOPE ID
Report Generated On: 08/26/2025 10:00 AM
| REPORT SUMMARY |  |  |  | REPORT DETAILS
| Total Billed Amount: | 1886.11 |  |  | Foreman: | Karl Guidroz
| Total Line Items: | 19 |  |  | Work Request #: | 89732091
| Billing Period: | 08/04/2025 to 08/10/25 |  |  | Scope ID #:
[5 empty] | Work Order #: | DCP0371513
[5 empty] | Customer: | AEP
[5 empty] | Job #: | 704-1
Thursday (08/07/2025)
Point Number | Billable Unit Code | Work Type | Unit Description | Unit of Measure | # Units | N/A | Pricing
Point 01 | CNC-SNB-10 | Inst | CNC,Splice Non-Tension Bare,#336-#1033 | EA | 1 |  | 20.29
Point 01 | CNC-SNB-2 | Inst | CNC,Splice Non-Tension Bare,#6-#2 | EA | 3 |  | 60.87
Point 01 | CND-SA10 | Inst | CND,Stirrup,Ampact,1/0 | EA | 2 |  | 24.98
Point 01 | CON-10-AAA-3-P | Inst | CON,#1/0 AWG,Alum Alloy,Three,Poly | FT | 102 |  | 73.44
Point 01 | SAA-DE-20-C | Inst | SAA,DE Clamp #4-2/0, Corr. | EA | 1 |  | 55.18
Point 01 | SVC-2-TP-ALA-RS | Tran | SVC,#2 AWG,Trip,Alum/Aly Neut,Res | EA | 1 |  | 195.83
Point 01 | SVD-3-CV-C | Tran | SVD,3 inch,Clevis,Corr | EA | 1 |  | 46.72
Point 02 | ANC-SHM-10-84-T1-C | Rem | ANC,Sgl Hlx Mach,10in,84in,TpEye 1in,Cor | EA | 1 |  | 28.6
Point 02 | SAA-DE-20-C | Rem | SAA,DE Clamp #4-2/0, Corr. | EA | 2 |  | 34.4
Point 02 | SWI-27-CO1-100-H-C | Rem | SWI,27kV,Line Cutout 1PH,100A,Hook,C | EA | 2 |  | 53.04
Point 04 | GND-CR-4 | Rem | GND,Cu Clad Rod,#4 | EA | 1 |  | 60.43
Point 04 | XFR-25-72-120-1B-S | Rem | XFR,25KVA,7.2/12.4kVY,120/240,1BG,SS | EA | 1 |  | 159
Point 05 | SVC-2-TP-ALA-RS | Tran | SVC,#2 AWG,Trip,Alum/Aly Neut,Res | EA | 1 |  | 195.83
Point 05 | SVD-3-CV | Tran | SVD,3 inch,Clevis | EA | 1 |  | 46.72
Point 06 | ANC-SHM-10-84-T1-C | Rem | ANC,Sgl Hlx Mach,10in,84in,TpEye 1in,Cor | EA | 1 |  | 28.6
Point 01 | SVD-SG10 | Inst | SVD, Service Grip, 1/0 | EA | 2 |  | 572.5
Point 01 | CNC-HTA-10 | Inst | Compression connector H-Tap Assembly 1/0 | EA | 8 |  | 76.56
TOTAL | [6 empty] | 1732.99
Friday (08/08/2025)
Point Number | Billable Unit Code | Work Type | Unit Description | Unit of Measure | # Units | N/A | Pricing
Point 05 | CNC-HTA-10 | Inst | Compression connector H-Tap Assembly 1/0 | EA | 8 |  | 76.56
Point 01 | CNC-HTA-10 | Inst | Compression connector H-Tap Assembly 1/0 | EA | 8 |  | 76.56
TOTAL | [6 empty] | 153.12